## Sheet1
ORION WBS Details |  |  |  | All in k$ |  |  | 2002-04-12 | Compiled by R.J. Noble |  |  | DRAFT ONLY, Indirects at Weighted Avg. 18 %
|  |  | Contingency Percentage | Total | Level 2 |  | Level 3 | Level 4 | Level 5/6 | SLAC |  | Collaborator | Needed | Levels 0, 1, 2
|  |  | of Total WBS = | WBS | Costs |  | Costs | Costs | Costs | Contribution |  | Contribution | Budget | Contingencies
|  |  | 0.17863 | 8928.6723 | [5 empty] | 1262.878 |  | 243.675 | 7422.1193 | 1594.8917
1 Accelerator Systems |  |  |  | 6017.1515 | [5 empty] | 1048.4028 |  | 243.675 | 4725.0738 | 1184.2764
| 1.1 Injector System |  |  |  | 573.5346 |  |  |  |  | 112.3998 |  | 45.675 | 415.4598 | 107.5494
|  | 1.1.1 RF Gun |  |  |  | Concert enclosure blks | 78.1425 |  |  | 19.8 |  | 33.675 | 24.6675
|  |  | 1.1.1.1 B&H |  |  |  |  | 72.45 |  | 19.8 |  | 33.675 | 18.975
|  |  | 1.1.1.1.1 SLAC Contribution | [5 empty] | 19.8
|  |  | 1.1.1.1.1.1 Copper | [5 empty] | 1
|  |  | 1.1.1.1.1.2 Stainless Steel | [5 empty] | 1
|  |  | 1.1.1.1.1.3 RF Waveguide Window | [5 empty] | 7.5
|  |  | 1.1.1.1.1.4 UV Windows (2) | [5 empty] | 4.4
|  |  | 1.1.1.1.1.5 Vacuum Flexible Hosing | [5 empty] | 0.5
|  |  | 1.1.1.1.1.6 SS (316L) Flanges | [5 empty] | 1
|  |  | 1.1.1.1.1.7 Metal In-Line Valves (3) | [5 empty] | 2.4
|  |  | 1.1.1.1.1.8 Mg Cathode | [5 empty] | 2
|  |  | 1.1.1.1.2 Collaborator Contribution | [5 empty] | 33.675
|  |  | 1.1.1.1.2.1 Machine, Tune Body - UCLA | [5 empty] | 33.275
|  |  | 1.1.1.1.2.2 Machine Cathode Plate-UCLA | [5 empty] | 0.4
|  |  | 1.1.1.1.3 New B&H | [5 empty] | 18.975
|  |  | 1.1.1.1.3.1 Mach, Cln, Braze, Leak Chk Gun | [5 empty] | 11.475
|  |  | 1.1.1.1.3.2 RF Tuners (2) | [5 empty] | 3
|  |  | 1.1.1.1.3.3 Gun Support/Stand | [5 empty] | 4.5
|  |  | 1.1.1.2 Contingency |  |  |  |  | 5.6925 |  | 0 |  | 0 | 5.6925
|  |  | 1.1.1.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.1.1.2.2 Collaborator Contribution | [5 empty] | 0
|  |  | 1.1.1.2.3 New Contingency | [5 empty] | 5.6925
|  | 1.1.2 Solenoid and Power Supply |  |  |  | Crane rental for 60' roof block | 61 |  |  | 39.5 |  | 12 | 9.5
|  |  | 1.1.2.1 B&H |  |  |  |  | 58 |  | 39.5 |  | 12 | 6.5
|  |  | 1.1.2.1.1 SLAC Contribution | [5 empty] | 39.5
|  |  | 1.1.2.1.1.1 Power Supply | [5 empty] | 25
|  |  | 1.1.2.1.1.2 Surplus GTF Coils (8) | [5 empty] | 14
|  |  | 1.1.2.1.1.3 Magnet Steel | [5 empty] | 0.5
|  |  | 1.1.2.1.2 Collaborator Contribution | [5 empty] | 12
|  |  | 1.1.2.1.2.1 Steel Machining-UCLA | [5 empty] | 12
|  |  | 1.1.2.1.3 New B&H | [5 empty] | 6.5
|  |  | 1.1.2.1.3.1 Deflecting Magnet | [5 empty] | 4.5
|  |  | 1.1.2.1.3.2 Girder/Supports | [5 empty] | 2
|  |  | 1.1.2.2 Contingency |  |  |  |  | 3 |  | 0 |  | 0 | 3
|  |  | 1.1.2.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.1.2.2.2 Collaborator Contribution | [5 empty] | 0
|  |  | 1.1.2.2.3 New Contingency | [5 empty] | 3
|  | 1.1.3 Diagnostics |  |  |  | Paint enclosure | 142.94 |  |  | 18.2 |  | 0 | 124.74
|  |  | 1.1.3.1 B&H |  |  |  |  | 107.3 |  | 18.2 |  | 0 | 89.1
|  |  | 1.1.3.1.1 SLAC Contribution | [5 empty] | 18.2
|  |  | 1.1.3.1.1.1 6-Way Port Cubes (3) | [5 empty] | 2
|  |  | 1.1.3.1.1.2 Linear Step Motor/Control (3) | [5 empty] | 4
|  |  | 1.1.3.1.1.3 Ceramic Vacuum Breaks | [5 empty] | 0.7
|  |  | 1.1.3.1.1.4 200,20 l/s Vac Pumps | [5 empty] | 4
|  |  | 1.1.3.1.1.5 All-Met. Gate Valves (2) | [5 empty] | 1.6
|  |  | 1.1.3.1.1.6 Met. In-Line Valves (2-b.line) | [5 empty] | 3.5
|  |  | 1.1.3.1.1.7 Met. In-Line Valves (3-ls.port) | [5 empty] | 2.4
|  |  | 1.1.3.1.2 Collaborator Contribution | [5 empty] | 0
|  |  | 1.1.3.1.3 New B&H | [5 empty] | 89.1
|  |  | 1.1.3.1.3.1 Phosphor Screens (2) | [5 empty] | 4
|  |  | 1.1.3.1.3.2 Currnet Toroids (2) | [5 empty] | 14
|  |  | 1.1.3.1.3.3 Faraday Cups (2) | [5 empty] | 4
|  |  | 1.1.3.1.3.4 XY Steering Magnets (4) | [5 empty] | 4
|  |  | 1.1.3.1.3.5 UV Windows (3) | [5 empty] | 6.6
|  |  | 1.1.3.1.3.6 Diagn. Line Vac. Pump. Sta. | [5 empty] | 6.5
|  |  | 1.1.3.1.3.7 Upgrade NLCTA Diagnostics | [5 empty] | 50
|  |  | 1.1.3.2 Contingency |  |  |  |  | 35.64 |  | 0 |  | 0 | 35.64
|  |  | 1.1.2.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.1.2.2.2 Collaborator Contribution | [5 empty] | 0
|  |  | 1.1.2.2.3 New Contingency | [5 empty] | 35.64
|  | 1.1.4 Labor and Installation |  |  |  |  | 291.4521 |  |  | 34.8998 |  | 0 | 256.5523
|  |  | 1.1.4.1 SLAC Contribution |  |  |  |  | 30.8873 |  | 30.8873 |  | 0 | 0
|  |  | 1.1.4.1.1 ARDB Physicist (215 h) | [5 empty] | 13.3751
|  |  | 1.1.4.1.2 Designer/Drafter (281.5 h) | [5 empty] | 17.5121
|  |  | 1.1.4.2 New Labor |  |  |  |  | 197.348 |  | 0 |  | 0 | 197.348
|  |  | 1.1.4.2.1 Engineer (215 h) | [5 empty] | 13.3751
|  |  | 1.1.4.2.2 Design/Drafter (180 h) | [5 empty] | 11.1978
|  |  | 1.1.4.2.3 Programmer (1000 h) | [5 empty] | 62.21
|  |  | 1.1.4.2.4 Technician (1000 h) | [5 empty] | 62.21
|  |  | 1.1.4.2.5 Alignment (210 h) | [5 empty] | 13.0641
|  |  | 1.1.4.2.6 Plumbing (120 h) | [5 empty] | 7.4652
|  |  | 1.1.4.2.7 Electrical Connection (170 h) | [5 empty] | 10.5757
|  |  | 1.1.4.2.8 Shop (230 h) | [5 empty] | 17.25
|  |  | 1.1.4.3 Contingency |  |  |  |  | 63.2169 |  | 4.0125 |  | 0 | 59.2044
|  |  | 1.1.4.3.1 SLAC Contribution | [5 empty] | 4.0125
|  |  | 1.1.4.3.2 New Contingency | [5 empty] | 59.2044
| 1.2 Laser System |  |  |  | 884.8587 |  |  |  |  | 274.4365 |  | 0 | 610.4222 | 153.6597
|  | 1.2.1 Ti:Sapphire Laser |  |  |  | Concert enclosure blks | 503.8 |  |  | 158 |  | 0 | 345.8
|  |  | 1.2.1.1 B&H |  |  |  |  | 424 |  | 158 |  | 0 | 266
|  |  | 1.2.1.1.1 SLAC Contribution | [5 empty] | 158
|  |  | 1.2.1.1.1.1 Oscillator | [5 empty] | 158
|  |  | 1.2.1.1.2 New B&H | [5 empty] | 266
|  |  | 1.2.1.1.2.1 Amplifier | [5 empty] | 266
|  |  | 1.2.1.2 Contingency |  |  |  |  | 79.8 |  | 0 |  | 0 | 79.8
|  |  | 1.2.1.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.2.1.2.2 New Contingency | [5 empty] | 79.8
|  | 1.2.2 Optical Components |  |  |  | Paint enclosure | 56 |  |  | 30 |  | 0 | 26
|  |  | 1.2.2.1 B&H |  |  |  |  | 50 |  | 30 |  | 0 | 20
|  |  | 1.2.2.1.1 SLAC Contribution | [5 empty] | 30
|  |  | 1.2.2.1.1.1 Mirrors | [5 empty] | 24
|  |  | 1.2.2.1.1.2 Lenses | [5 empty] | 4
|  |  | 1.2.2.1.1.3 Filters | [5 empty] | 2
|  |  | 1.2.2.1.2 New B&H | [5 empty] | 20
|  |  | 1.2.2.1.2.1 Mirrors | [5 empty] | 16
|  |  | 1.2.2.1.2.2 Lenses | [5 empty] | 2
|  |  | 1.2.2.1.2.3 Filters | [5 empty] | 2
|  |  | 1.2.2.2 Contingency |  |  |  |  | 6 |  | 0 |  | 0 | 6
|  |  | 1.2.2.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.2.2.1.1 New Contingency | [5 empty] | 6
|  | 1.2.3 Optomechanical Components |  |  |  | Seal joints | 104.4 |  |  | 16 |  | 0 | 88.4
|  |  | 1.2.3.1 B&H |  |  |  |  | 84 |  | 16 |  | 0 | 68
|  |  | 1.2.3.1.1 SLAC Contribution | [5 empty] | 16
|  |  | 1.2.3.1.1.1 Optical Tables (2) | [5 empty] | 16
|  |  | 1.2.3.1.2 New B&H | [5 empty] | 68
|  |  | 1.2.3.1.2.1 Optical Table | [5 empty] | 8
|  |  | 1.2.3.1.2.2 Optical mounts, fixtures | [5 empty] | 60
|  |  | 1.2.3.2 Contingency |  |  |  |  | 20.4 |  | 0 |  | 0 | 20.4
|  |  | 1.2.3.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.2.3.2.2 New Contingency | [5 empty] | 20.4
|  | 1.2.4 Diagnostics |  |  |  |  | 67 |  |  | 30 |  | 0 | 37
|  |  | 1.2.4.1 B&H |  |  |  |  | 55 |  | 30 |  | 0 | 25
|  |  | 1.2.4.1.1 SLAC Contribution (detail?) | [5 empty] | 30
|  |  | 1.2.4.1.2 New B&H (detail?) | [5 empty] | 25
|  |  | 1.2.4.2 Contingency |  |  |  |  | 12 |  | 0 |  | 0 | 12
|  |  | 1.2.4.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.2.4.1.2 New Contingency | [5 empty] | 12
|  | 1.2.5 Labor and Installation |  |  |  |  | 153.6587 |  |  | 40.4365 |  | 0 | 113.2222
|  |  | 1.2.5.1 SLAC Contribution |  |  |  |  | 31.105 |  | 31.105 |  | 0 | 0
|  |  | 1.2.5.1.1 ARDB Physicist (500 h) | [5 empty] | 31.105
|  |  | 1.2.5.2 New Labor |  |  |  |  | 87.094 |  | 0 |  | 0 | 87.094
|  |  | 1.2.5.2.1 Engineer (45 h) | [5 empty] | 2.7994
|  |  | 1.2.5.2.2 Designer/Drafter (45 h) | [5 empty] | 2.7994
|  |  | 1.2.5.2.3 Technician (570 h) | [5 empty] | 35.4597
|  |  | 1.2.5.2.4 Alignment (240 h) | [5 empty] | 14.9304
|  |  | 1.2.5.2.5 Plumbing (45 h) | [5 empty] | 2.7994
|  |  | 1.2.5.2.6 Electrical Connection (193 h) | [5 empty] | 12.0065
|  |  | 1.2.5.2.7 Shop (262 h) | [5 empty] | 16.299
|  |  | 1.2.5.3 Contingency |  |  |  |  | 35.4597 |  | 9.3315 |  | 0 | 26.1282
|  |  | 1.2.5.3.1 SLAC Contribution | [5 empty] | 9.3315
|  |  | 1.2.5.3.2 New Contingency | [5 empty] | 26.1282
| 1.3 Radio Frequency Power System |  |  |  | 1057.3346 |  |  |  |  | 509.4008 |  | 0 | 547.9338 | 160.7387
|  | 1.3.1 High Voltage System |  |  |  |  | 200 |  |  | 200 |  | 0 | 0
|  |  | 1.3.1.1 B&H |  |  |  |  | 200 |  | 200 |  | 0 | 0
|  |  | 1.3.1.1.1 SLAC Contribution | [5 empty] | 200
|  |  | 1.3.1.1.1.1 Klystron | [5 empty] | 120
|  |  | 1.3.1.1.1.2 Pulse Transformer | [5 empty] | 40
|  |  | 1.3.1.1.1.3 Solenoid | [5 empty] | 40
|  |  | 1.3.1.2 Contingency |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.3.1.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.3.1.2.2 New Contingency | [5 empty] | 0
|  | 1.3.2 Power Supply System |  |  |  |  | 130 |  |  | 130 |  | 0 | 0
|  |  | 1.3.2.1 B&H |  |  |  |  | 100 |  | 100 |  | 0 | 0
|  |  | 1.3.2.1.1 SLAC Contribution | [5 empty] | 100
|  |  | 1.3.2.1.1.1 Modulator | [5 empty] | 80
|  |  | 1.3.2.1.1.2 Charging Supply | [5 empty] | 20
|  |  | 1.3.2.2 Contingency |  |  |  |  | 30 |  | 30 |  | 0 | 0
|  |  | 1.3.2.2.1 SLAC Contribution | [5 empty] | 30
|  |  | 1.3.2.2.2 New Contingency | [5 empty] | 0
|  | 1.3.3 Low-Level RF and Drive |  |  |  |  | 92 |  |  | 53 |  | 0 | 39
|  |  | 1.3.3.1 B&H |  |  |  |  | 83 |  | 53 |  | 0 | 30
|  |  | 1.3.3.1.1 SLAC Contribution | [5 empty] | 53
|  |  | 1.3.3.1.1.1 Master Oscillator | [5 empty] | 23
|  |  | 1.3.3.1.1.2 S-Band TWT (SBIR) | [5 empty] | 30
|  |  | 1.3.3.1.2 New B&H | [5 empty] | 30
|  |  | 1.3.3.1.2.1 Fault Protection | [5 empty] | 6
|  |  | 1.3.3.1.2.2 Interlock System | [5 empty] | 12
|  |  | 1.3.3.1.2.3 Low-Level RF System | [5 empty] | 12
|  |  | 1.3.3.2 Contingency |  |  |  |  | 9 |  | 0 |  | 0 | 9
|  |  | 1.3.3.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.3.3.2.2 New Contingency | [5 empty] | 9
|  | 1.3.4 Waveguide System |  |  |  |  | 107.8 |  |  | 107.8 |  | 0 | 0
|  |  | 1.3.4.1 B&H |  |  |  |  | 107.8 |  | 107.8 |  | 0 | 0
|  |  | 1.3.4.1.1 SLAC Contribution | [5 empty] | 107.8
|  |  | 1.3.4.1.1.1 E-Bends (2) | [5 empty] | 9
|  |  | 1.3.4.1.1.2 H-Bends (2) | [5 empty] | 9
|  |  | 1.3.4.1.1.3 3-dB Coupler | [5 empty] | 7
|  |  | 1.3.4.1.1.4 High Power Loads (2) | [5 empty] | 17.3
|  |  | 1.3.4.1.1.5 Magic Tee Power Splitter | [5 empty] | 10
|  |  | 1.3.4.1.1.6 High Power Phase Shifter | [5 empty] | 15
|  |  | 1.3.4.1.1.7 50-dB Coupler Diagnostics | [5 empty] | 7.5
|  |  | 1.3.4.1.1.8 RF Window | [5 empty] | 7.2
|  |  | 1.3.4.1.1.9 W/G Pumping Stations | [5 empty] | 4.3
|  |  | 1.3.4.1.1.10 Vacuum Pumping Station | [5 empty] | 6.5
|  |  | 1.3.4.1.1.11 High Power Var. Attenuator | [5 empty] | 15
|  |  | 1.3.4.2 Contingency |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.3.4.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.3.4.2.2 New Contingency | [5 empty] | 0
|  | 1.3.5 Labor and Installation |  |  |  |  | 527.5346 |  |  | 18.6008 |  | 0 | 508.9338
|  |  | 1.3.5.1 SLAC Contribution |  |  |  |  | 14.3083 |  | 14.3083 |  | 0 | 0
|  |  | 1.3.5.1.1 ARDB Physicist (230 h) | [5 empty] | 14.3083
|  |  | 1.3.5.2 New Labor |  |  |  |  | 391.4875 |  | 0 |  | 0 | 391.4875
|  |  | 1.3.5.2.1 Engineer (588 h) | [5 empty] | 36.5795
|  |  | 1.3.5.2.2 Designer/Drafter (275 h) | [5 empty] | 17.1077
|  |  | 1.3.5.2.3 Programmer (640 h) | [5 empty] | 39.8144
|  |  | 1.3.5.2.4 Technician (4000 h) | [5 empty] | 248.84
|  |  | 1.3.5.2.5 Alignment (60 h) | [5 empty] | 3.7326
|  |  | 1.3.5.2.6 Plumbing (190 h) | [5 empty] | 11.8199
|  |  | 1.3.5.2.7 Electrical Connection (170 h) | [5 empty] | 10.5757
|  |  | 1.3.5.2.8 Shop (370 h) | [5 empty] | 23.0177
|  |  | 1.2.5.3 Contingency |  |  |  |  | 121.7387 |  | 4.2925 |  | 0 | 117.4463
|  |  | 1.2.5.3.1 SLAC Contribution | [5 empty] | 4.2925
|  |  | 1.2.5.3.2 New Contingency | [5 empty] | 117.4463
| 1.4 Low Energy Beam Lines |  |  |  | 1394.5263 |  |  |  |  | 67.529 |  | 198 | 1128.9974 | 276.1215
|  | 1.4.1 Magnets |  |  |  |  | 577.05 |  |  | 0 |  | 150 | 427.05
|  |  | 1.4.1.1 B&H |  |  |  |  | 478.5 |  | 0 |  | 150 | 328.5
|  |  | 1.4.1.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.1.1.2 Collaborator Contribution | [5 empty] | 150
|  |  | 1.4.1.1.2.1 Spectrometer (1) | [5 empty] | 150
|  |  | 1.4.1.1.3 New B&H | [5 empty] | 328.5
|  |  | 1.4.1.1.3.1 Dipole Magnets (6) | [5 empty] | 45
|  |  | 1.4.1.1.3.2 Quadrupole Magnets (30) | [5 empty] | 126
|  |  | 1.4.1.1.3.3 Steer. & Corr. Magnets (15) | [5 empty] | 7.5
|  |  | 1.4.1.1.3.4 Spectrometers (1) | [5 empty] | 150
|  |  | 1.4.1.2 Contingency |  |  |  |  | 98.55 |  | 0 |  | 0 | 98.55
|  |  | 1.4.1.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.1.2.2 New Contingency | [5 empty] | 98.55
|  | 1.4.2 Power Supplies |  |  |  |  | 236.6 |  |  | 0 |  | 0 | 236.6
|  |  | 1.4.2.1 B&H |  |  |  |  | 182 |  | 0 |  | 0 | 182
|  |  | 1.4.2.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.2.1.2 New B&H | [5 empty] | 182
|  |  | 1.4.2.1.2.1 Dip. & Quad. Supplies (38) | [5 empty] | 152
|  |  | 1.4.2.1.2.2 Steer. & Corr. Supplies (15) | [5 empty] | 30
|  |  | 1.4.2.2 Contingency |  |  |  |  | 54.6 |  | 0 |  | 0 | 54.6
|  |  | 1.4.2.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.2.2.2 New Contingency | [5 empty] | 54.6
|  | 1.4.3 Diagnostics |  |  |  |  | 172.8 |  |  | 0 |  | 48 | 124.8
|  |  | 1.4.3.1 B&H |  |  |  |  | 144 |  | 0 |  | 48 | 96
|  |  | 1.4.3.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.3.1.2 Collaborator Contribution | [5 empty] | 48
|  |  | 1.4.3.1.2.1 Phosphor Screens (4) | [5 empty] | 8
|  |  | 1.4.3.1.2.2 Current Toroids (2) | [5 empty] | 14
|  |  | 1.4.3.1.2.3 Faraday Cup (1) | [5 empty] | 2
|  |  | 1.4.3.1.2.4 BPM (2) | [5 empty] | 24
|  |  | 1.4.3.1.3 New B&H | [5 empty] | 96
|  |  | 1.4.3.1.3.1 Phosphor Screens (8) | [5 empty] | 16
|  |  | 1.4.3.1.3.2 Current Toroids (4) | [5 empty] | 28
|  |  | 1.4.3.1.3.3 Faraday Cup (2) | [5 empty] | 4
|  |  | 1.4.3.1.3.4 BPM (4) | [5 empty] | 48
|  |  | 1.4.3.2 Contingency |  |  |  |  | 28.8 |  | 0 |  | 0 | 28.8
|  |  | 1.4.3.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.3.2.2 New Contingency | [5 empty] | 28.8
|  | 1.4.4 Vacuum System |  |  |  |  | 80.6325 |  |  | 0 |  | 0 | 80.6325
|  |  | 1.4.4.1 B&H |  |  |  |  | 62.025 |  | 0 |  | 0 | 62.025
|  |  | 1.4.4.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.4.1.2 New B&H | [5 empty] | 62.025
|  |  | 1.4.4.1.2.1 Pumping Stations (5) | [5 empty] | 35
|  |  | 1.4.4.1.2.2 1.5" ID Valves (5) | [5 empty] | 6
|  |  | 1.4.4.1.2.3 304 SST 1" & 1.5" Tubing | [5 empty] | 1
|  |  | 1.4.4.1.2.4 2.75" Conflat Nrot. Flange (50) | [5 empty] | 0.6
|  |  | 1.4.4.1.2.5 2.75" Conflat Rot. Flange (50) | [5 empty] | 0.8
|  |  | 1.4.4.1.2.6 Fastener/Gasket Sets (100) | [5 empty] | 2
|  |  | 1.4.4.1.2.7 Convoluted Bellows (55) | [5 empty] | 5.225
|  |  | 1.4.4.1.2.8 Welded Bellows (500) | [5 empty] | 5
|  |  | 1.4.4.1.2.9 Vacuum Gauges (5) | [5 empty] | 2
|  |  | 1.4.4.1.2.10 Assort. Vac. Tees & Crosses | [5 empty] | 2
|  |  | 1.4.4.1.2.11 Vacuum Windows (4) | [5 empty] | 2.4
|  |  | 1.4.4.2 Contingency |  |  |  |  | 18.6075 |  | 0 |  | 0 | 18.6075
|  |  | 1.4.4.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.4.2.2 New Contingency | [5 empty] | 18.6075
|  | 1.4.5 Cooling System |  |  |  |  | 32.5 |  |  | 0 |  | 0 | 32.5
|  |  | 1.4.5.1 B&H |  |  |  |  | 25 |  | 0 |  | 0 | 25
|  |  | 1.4.5.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.5.1.2 New B&H (E163 est) | [5 empty] | 25
|  |  | 1.4.5.2 Contingency |  |  |  |  | 7.5 |  | 0 |  | 0 | 7.5
|  |  | 1.4.5.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.4.5.2.2 New Contingency | [5 empty] | 7.5
|  | 1.4.9 Labor and Installation |  |  |  |  | 294.9438 |  |  | 67.529 |  | 0 | 227.4149
|  |  | 1.4.9.1 SLAC Contribution |  |  |  |  | 51.9453 |  | 51.9453 |  | 0 | 0
|  |  | 1.4.9.1.1 ARDB Physicist (835 h) | [5 empty] | 51.9453
|  |  | 1.4.9.2 New Labor |  |  |  |  | 174.9345 |  | 0 |  | 0 | 174.9345
|  |  | 1.4.9.2.1 Engineer (530 h) | [5 empty] | 32.9713
|  |  | 1.4.9.2.2 Designer/Drafter (152 h) | [5 empty] | 9.4559
|  |  | 1.4.9.2.3 Programmer (190 h) | [5 empty] | 11.8199
|  |  | 1.4.9.2.4 Technician (740 h) | [5 empty] | 46.0354
|  |  | 1.4.9.2.5 Alignment (120 h) | [5 empty] | 7.4652
|  |  | 1.4.9.2.6 Plumbing (40 h) | [5 empty] | 2.4884
|  |  | 1.4.9.2.7 Electrical Connection (130 h) | [5 empty] | 8.0873
|  |  | 1.4.9.2.8 Shop (910 h) | [5 empty] | 56.6111
|  |  | 1.4.9.3 Contingency |  |  |  |  | 68.064 |  | 15.5836 |  | 0 | 52.4804
|  |  | 1.4.9.3.1 SLAC Contribution | [5 empty] | 15.5836
|  |  | 1.4.9.3.2 New Contingency | [5 empty] | 52.4804
| 1.5 High Energy Beam Lines |  |  |  | 856.5958 |  |  |  |  | 67.529 |  | 0 | 789.0669 | 197.676
|  | 1.5.1 Magnets |  |  |  |  | 301.6 |  |  | 0 |  | 0 | 301.6
|  |  | 1.5.1.1 B&H |  |  |  |  | 232 |  | 0 |  | 0 | 232
|  |  | 1.5.1.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.1.1.2 Collaborator Contribution | [5 empty] | 0
|  |  | 1.5.1.1.3 New B&H | [5 empty] | 232
|  |  | 1.5.1.1.3.1 Dipole Magnets (2) | [5 empty] | 15
|  |  | 1.5.1.1.3.2 Quadrupole Magnets (15) | [5 empty] | 63
|  |  | 1.5.1.1.3.3 Steer. & Corr. Magnets (8) | [5 empty] | 4
|  |  | 1.5.1.1.3.4 Spectrometers (1) | [5 empty] | 150
|  |  | 1.5.1.2 Contingency |  |  |  |  | 69.6 |  | 0 |  | 0 | 69.6
|  |  | 1.5.1.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.1.2.2 New Contingency | [5 empty] | 69.6
|  | 1.5.2 Power Supplies |  |  |  |  | 114.4 |  |  | 0 |  | 0 | 114.4
|  |  | 1.5.2.1 B&H |  |  |  |  | 88 |  | 0 |  | 0 | 88
|  |  | 1.5.2.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.2.1.2 New B&H | [5 empty] | 88
|  |  | 1.5.2.1.2.1 Dip. & Quad. Supplies (18) | [5 empty] | 72
|  |  | 1.5.2.1.2.2 Steer. & Corr. Supplies (8) | [5 empty] | 16
|  |  | 1.5.2.2 Contingency |  |  |  |  | 26.4 |  | 0 |  | 0 | 26.4
|  |  | 1.5.2.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.2.2.2 New Contingency | [5 empty] | 26.4
|  | 1.5.3 Diagnostics |  |  |  |  | 62.4 |  |  | 0 |  | 0 | 62.4
|  |  | 1.5.3.1 B&H |  |  |  |  | 48 |  | 0 |  | 0 | 48
|  |  | 1.5.3.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.3.1.3 New B&H | [5 empty] | 48
|  |  | 1.5.3.1.3.1 Phosphor Screens (4) | [5 empty] | 8
|  |  | 1.5.3.1.3.2 Current Toroids (2) | [5 empty] | 14
|  |  | 1.5.3.1.3.3 Faraday Cup (1) | [5 empty] | 2
|  |  | 1.5.3.1.3.4 BPM (2) | [5 empty] | 24
|  |  | 1.5.3.2 Contingency |  |  |  |  | 14.4 |  | 0 |  | 0 | 14.4
|  |  | 1.5.3.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.3.2.2 New Contingency | [5 empty] | 14.4
|  | 1.5.4 Vacuum System |  |  |  |  | 50.752 |  |  | 0 |  | 0 | 50.752
|  |  | 1.5.4.1 B&H |  |  |  |  | 39.04 |  | 0 |  | 0 | 39.04
|  |  | 1.5.4.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.4.1.2 New B&H | [5 empty] | 39.04
|  |  | 1.5.4.1.2.1 Pumping Stations (3) | [5 empty] | 21
|  |  | 1.5.4.1.2.2 1.5" ID Valves (3) | [5 empty] | 3.6
|  |  | 1.5.4.1.2.3 304 SST 1" & 1.5" Tubing | [5 empty] | 1
|  |  | 1.5.4.1.2.4 2.75" Conflat Nrot. Flange (30) | [5 empty] | 0.36
|  |  | 1.5.4.1.2.5 2.75" Conflat Rot. Flange (30) | [5 empty] | 0.48
|  |  | 1.5.4.1.2.6 Fastener/Gasket Sets (70) | [5 empty] | 1.4
|  |  | 1.5.4.1.2.7 Convoluted Bellows (40) | [5 empty] | 3.8
|  |  | 1.5.4.1.2.8 Welded Bellows (300) | [5 empty] | 3
|  |  | 1.5.4.1.2.9 Vacuum Gauges (3) | [5 empty] | 1.2
|  |  | 1.5.4.1.2.10 Assort. Vac. Tees & Crosses | [5 empty] | 2
|  |  | 1.5.4.1.2.11 Vacuum Windows (2) | [5 empty] | 1.2
|  |  | 1.5.4.2 Contingency |  |  |  |  | 11.712 |  | 0 |  | 0 | 11.712
|  |  | 1.5.4.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.4.2.2 New Contingency | [5 empty] | 11.712
|  | 1.5.5 Cooling System |  |  |  |  | 32.5 |  |  | 0 |  | 0 | 32.5
|  |  | 1.5.5.1 B&H |  |  |  |  | 25 |  | 0 |  | 0 | 25
|  |  | 1.5.5.1.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.5.1.2 New B&H (same as LE Hall) | [5 empty] | 25
|  |  | 1.5.5.2 Contingency |  |  |  |  | 7.5 |  | 0 |  | 0 | 7.5
|  |  | 1.5.5.2.1 SLAC Contribution | [5 empty] | 0
|  |  | 1.5.5.2.2 New Contingency | [5 empty] | 7.5
|  | 1.5.9 Labor and Installation |  |  |  |  | 294.9438 |  |  | 67.529 |  | 0 | 227.4149
|  |  | 1.5.9.1 SLAC Contribution |  |  |  |  | 51.9453 |  | 51.9453 |  | 0 | 0
|  |  | 1.5.9.1.1 ARDB Physicist (835 h) | [5 empty] | 51.9453
|  |  | 1.5.9.2 New Labor |  |  |  |  | 174.9345 |  | 0 |  | 0 | 174.9345
|  |  | 1.5.9.2.1 Engineer (530 h) | [5 empty] | 32.9713
|  |  | 1.5.9.2.2 Designer/Drafter (152 h) | [5 empty] | 9.4559
|  |  | 1.5.9.2.3 Programmer (190 h) | [5 empty] | 11.8199
|  |  | 1.5.9.2.4 Technician (740 h) | [5 empty] | 46.0354
|  |  | 1.5.9.2.5 Alignment (120 h) | [5 empty] | 7.4652
|  |  | 1.5.9.2.6 Plumbing (40 h) | [5 empty] | 2.4884
|  |  | 1.5.9.2.7 Electrical Connection (130 h) | [5 empty] | 8.0873
|  |  | 1.5.9.2.8 Shop (910 h) | [5 empty] | 56.6111
|  |  | 1.5.9.3 Contingency |  |  |  |  | 68.064 |  | 15.5836 |  | 0 | 52.4804
|  |  | 1.5.9.3.1 SLAC Contribution | [5 empty] | 15.5836
|  |  | 1.5.9.3.2 New Contingency | [5 empty] | 52.4804
| 1.6 Protection Systems |  |  |  | 686.8714 |  |  |  |  | 0 |  | 0 | 686.8714 | 158.5088
|  | 1.6.1 Beam Containment (2 Halls) |  |  |  |  | 366.3286 |  |  | 0 |  | 0 | 366.3286
|  |  | 1.6.1.1 EDI |  |  |  |  | 14.9304 |  | 0 |  | 0 | 14.9304
|  |  | 1.6.1.1.1 Engineer (160 h) | [5 empty] | 9.9536
|  |  | 1.6.1.1.1 Designer/Drafter (80 h) | [5 empty] | 4.9768
|  |  | 1.6.1.2 B&H |  |  |  |  | 266.8608 |  | 0 |  | 0 | 266.8608
|  |  | 1.6.1.2.1 Average Current Monitors (6) | [5 empty] | 15
|  |  | 1.6.1.2.2 Current Toroids (6) | [5 empty] | 18
|  |  | 1.6.1.2.3 ACM p/s, crate, hardware (6) | [5 empty] | 6
|  |  | 1.6.1.2.4 BSOIC (8) | [5 empty] | 104
|  |  | 1.6.1.2.5 BCS Interlock Panel (2) | [5 empty] | 6
|  |  | 1.6.1.2.6 BCS cables, connectors (2) | [5 empty] | 6
|  |  | 1.6.1.2.7 Coord. Technician (160 h) | [5 empty] | 9.9536
|  |  | 1.6.1.2.8 Installer (320 h) | [5 empty] | 19.9072
|  |  | 1.6.1.2.9 Burn-Through Monitor (4) | [5 empty] | 2
|  |  | 1.6.1.2.10 Hall Entrance Beam Stop (4) | [5 empty] | 40
|  |  | 1.6.1.2.11 Terminating Beam Stops (4) | [5 empty] | 40
|  |  | 1.6.1.3 Contingency |  |  |  |  | 84.5374 |  | 0 |  | 0 | 84.5374
|  | 1.6.2 Machine Protection (2 Halls) |  |  |  |  | 100.2968 |  |  | 0 |  | 0 | 100.2968
|  |  | 1.6.2.1 EDI |  |  |  |  | 14.9304 |  | 0 |  | 0 | 14.9304
|  |  | 1.6.2.1.1 Engineer (160 h) | [5 empty] | 9.9536
|  |  | 1.6.2.1.1 Designer/Drafter (80 h) | [5 empty] | 4.9768
|  |  | 1.6.2.2 B&H |  |  |  |  | 62.221 |  | 0 |  | 0 | 62.221
|  |  | 1.6.2.2.1 Fast Closing Gate Valve (2) | [5 empty] | 36
|  |  | 1.6.2.2.2 Gate Valve Controller (2) | [5 empty] | 20
|  |  | 1.6.2.2.3 Coord. Technician (50 h) | [5 empty] | 3.1105
|  |  | 1.6.2.2.4 Installer (50 h) | [5 empty] | 3.1105
|  |  | 1.6.2.3 Contingency |  |  |  |  | 23.1454 |  | 0 |  | 0 | 23.1454
|  | 1.6.3 Personnel Protection |  |  |  |  | 220.246 |  |  | 0 |  | 0 | 220.246
|  |  | 1.6.3.1 EDI |  |  |  |  | 39.8144 |  | 0 |  | 0 | 39.8144
|  |  | 1.6.3.1.1 Engineer (160 h, Laser Rm) | [5 empty] | 9.9536
|  |  | 1.6.3.1.2 Des/Draft. (80 h, Laser Rm) | [5 empty] | 4.9768
|  |  | 1.6.3.1.3 Engineer (240 h, 2 Halls) | [5 empty] | 14.9304
|  |  | 1.6.3.1.2 Des/Draft. (160 h, 2 Halls) | [5 empty] | 9.9536
|  |  | 1.6.3.2 B&H |  |  |  |  | 129.6056 |  | 0 |  | 0 | 129.6056
|  |  | 1.6.3.2.1 Laser Rm PLC, I/O Modules | [5 empty] | 5
|  |  | 1.6.3.2.2 Laser Rm Status, Control Panels | [5 empty] | 3
|  |  | 1.6.3.2.3 Laser Rm & Linac Shutters | [5 empty] | 4
|  |  | 1.6.3.2.4 Laser Rm cables, switches, conn. | [5 empty] | 3
|  |  | 1.6.3.2.5 Coord. Technician (80 h, Laser Rm) | [5 empty] | 4.9768
|  |  | 1.6.3.2.6 Installer (320 h, Laser Rm) | [5 empty] | 19.9072
|  |  | 1.6.3.2.7 Expt Hall PPS Logic (2) | [5 empty] | 10
|  |  | 1.6.3.2.8 Expt Hall Status, Control Panels (2) | [5 empty] | 10
|  |  | 1.6.3.2.9 Expt Hall cables, switches, conn. (2) | [5 empty] | 10
|  |  | 1.6.3.2.10 Coord. Technician (320 h, 2 Halls) | [5 empty] | 19.9072
|  |  | 1.6.3.2.11 Installer (640 h, 2 Halls) | [5 empty] | 39.8144
|  |  | 1.6.3.3 Contingency |  |  |  |  | 50.826 |  | 0 |  | 0 | 50.826
| 1.7 Control System |  |  |  | 189.9401 |  |  |  |  | 17.1077 |  | 0 | 172.8323 | 43.8323
|  | 1.7.1 System Engineering and Integration |  |  |  |  | 57.3401 |  |  | 17.1077 |  | 0 | 40.2323
|  |  | 1.7.1.1 EDI |  |  |  |  | 44.1077 |  | 17.1077 |  | 0 | 27
|  |  | 1.7.1.2 B&H |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.7.1.3 Contingency |  |  |  |  | 13.2323 |  | 0 |  | 0 | 13.2323
|  | 1.7.2 Vax Multibus Interface |  |  |  |  | 26 |  |  | 0 |  | 0 | 26
|  |  | 1.7.2.1 EDI |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.7.2.2 B&H |  |  |  |  | 20 |  | 0 |  | 0 | 20
|  |  | 1.7.2.3 Contingency |  |  |  |  | 6 |  | 0 |  | 0 | 6
|  | 1.7.3 Micro System |  |  |  |  | 11.7 |  |  | 0 |  | 0 | 11.7
|  |  | 1.7.3.1 EDI |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.7.3.2 B&H |  |  |  |  | 9 |  | 0 |  | 0 | 9
|  |  | 1.7.3.3 Contingency |  |  |  |  | 2.7 |  | 0 |  | 0 | 2.7
|  | 1.7.4 Camac System |  |  |  |  | 68.9 |  |  | 0 |  | 0 | 68.9
|  |  | 1.7.4.1 EDI |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.7.4.2 B&H |  |  |  |  | 53 |  | 0 |  | 0 | 53
|  |  | 1.7.4.3 Contingency |  |  |  |  | 15.9 |  | 0 |  | 0 | 15.9
|  | 1.7.5 Signal Processing |  |  |  |  | 14.3 |  |  | 0 |  | 0 | 14.3
|  |  | 1.7.5.1 EDI |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.7.5.2 B&H |  |  |  |  | 11 |  | 0 |  | 0 | 11
|  |  | 1.7.5.3 Contingency |  |  |  |  | 3.3 |  | 0 |  | 0 | 3.3
|  | 1.7.6 Timing System |  |  |  |  | 6.5 |  |  | 0 |  | 0 | 6.5
|  |  | 1.7.6.1 EDI |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.7.6.2 B&H |  |  |  |  | 5 |  | 0 |  | 0 | 5
|  |  | 1.7.6.3 Contingency |  |  |  |  | 1.5 |  | 0 |  | 0 | 1.5
|  | 1.7.7 Interlock Power and Trunking |  |  |  |  | 5.2 |  |  | 0 |  | 0 | 5.2
|  |  | 1.7.7.1 EDI |  |  |  |  | 0 |  | 0 |  | 0 | 0
|  |  | 1.7.7.2 B&H |  |  |  |  | 4 |  | 0 |  | 0 | 4
|  |  | 1.7.7.3 Contingency |  |  |  |  | 1.2 |  | 0 |  | 0 | 1.2
| 1.8 Cable Plant |  |  |  | 373.49 |  |  |  |  | 0 |  | 0 | 373.49 | 86.19
|  | 1.8.1 Cable |  |  |  | Cores | 280.54 |  |  | 0 |  | 0 | 280.54
|  |  | 1.8.1.1 EDI |  |  |  |  | 49.8 |  | 0 |  | 0 | 49.8
|  |  | 1.8.1.2 B&H |  |  |  |  | 166 |  | 0 |  | 0 | 166
|  |  | 1.8.1.3 Contingency |  |  |  |  | 64.74 |  | 0 |  | 0 | 64.74
|  | 1.8.2 Cable Trays (335 ft.) |  |  |  | Trim coils | 25.35 |  |  | 0 |  | 0 | 25.35
|  |  | 1.8.2.1 EDI |  |  |  |  | 4.5 |  | 0 |  | 0 | 4.5
|  |  | 1.8.2.2 B&H |  |  |  |  | 15 |  | 0 |  | 0 | 15
|  |  | 1.8.2.3 Contingency |  |  |  |  | 5.85 |  | 0 |  | 0 | 5.85
|  | 1.8.3 Relay Racks |  |  |  |  | 67.6 |  |  | 0 |  | 0 | 67.6
|  |  | 1.8.3.1 EDI |  |  |  |  | 12 |  | 0 |  | 0 | 12
|  |  | 1.8.3.2 B&H |  |  |  |  | 40 |  | 0 |  | 0 | 40
|  |  | 1.8.3.3 Contingency |  |  |  |  | 15.6 |  | 0 |  | 0 | 15.6
2 Conventional Construction |  |  |  | 1564.8578 | [5 empty] | 0 |  | 0 | 1564.8578 | 361.121
| 2.1 Laser Room 1 |  |  |  | 170.2698 |  |  |  |  | 0 |  | 0 | 170.2698 | 39.293
|  | 2.1.1 Enclosure (500 sq. ft.) |  |  |  |  | 136.4698 |  |  | 0 |  | 0 | 136.4698
|  |  | 2.1.1.1 EDI |  |  |  |  | 4.9768 |  | 0 |  | 0 | 4.9768
|  |  | 2.1.1.2 B&H |  |  |  |  | 100 |  | 0 |  | 0 | 100
|  |  | 2.1.1.3 Contingency |  |  |  |  | 31.493 |  | 0 |  | 0 | 31.493
|  | 2.1.2 Optical Transport Lines |  |  |  |  | 33.8 |  |  | 0 |  | 0 | 33.8
|  |  | 2.1.2.1 EDI |  |  |  |  | 6 |  | 0 |  | 0 | 6
|  |  | 2.1.2.2 B&H |  |  |  |  | 20 |  | 0 |  | 0 | 20
|  |  | 2.1.2.3 Contingency |  |  |  |  | 7.8 |  | 0 |  | 0 | 7.8
| 2.2 Laser Room 2 |  |  |  | 270.4 |  |  |  |  | 0 |  | 0 | 270.4 | 62.4
|  | 2.2.1 Entry Vestibule (50 sq. ft.) |  |  |  |  | 16.9 |  |  | 0 |  | 0 | 16.9
|  |  | 2.2.1.1 EDI |  |  |  |  | 3 |  | 0 |  | 0 | 3
|  |  | 2.2.1.2 B&H |  |  |  |  | 10 |  | 0 |  | 0 | 10
|  |  | 2.2.1.3 Contingency |  |  |  |  | 3.9 |  | 0 |  | 0 | 3.9
|  | 2.2.2 User Enclosure 1 (375 sq. ft.) |  |  |  |  | 126.75 |  |  | 0 |  | 0 | 126.75
|  |  | 2.2.2.1 EDI |  |  |  |  | 22.5 |  | 0 |  | 0 | 22.5
|  |  | 2.2.2.2 B&H |  |  |  |  | 75 |  | 0 |  | 0 | 75
|  |  | 2.2.2.3 Contingency |  |  |  |  | 29.25 |  | 0 |  | 0 | 29.25
|  | 2.2.3 User Enclosure 2 (375 sq. ft.) |  |  |  |  | 126.75 |  |  | 0 |  | 0 | 126.75
|  |  | 2.2.3.1 EDI |  |  |  |  | 22.5 |  | 0 |  | 0 | 22.5
|  |  | 2.2.3.2 B&H |  |  |  |  | 75 |  | 0 |  | 0 | 75
|  |  | 2.2.3.3 Contingency |  |  |  |  | 29.25 |  | 0 |  | 0 | 29.25
| 2.3 Low Energy Hall |  |  |  | 449.54 |  |  |  |  | 0 |  | 0 | 449.54 | 103.74
|  | 2.3.1 Low Energy Hall |  |  |  |  | 449.54 |  |  | 0 |  | 0 | 449.54
|  |  | 2.3.1.1 EDI |  |  |  |  | 79.8 |  | 0 |  | 0 | 79.8
|  |  | 2.3.1.2 B&H |  |  |  |  | 266 |  | 0 |  | 0 | 266
|  |  | 2.3.1.3 Contingency |  |  |  |  | 103.74 |  | 0 |  | 0 | 103.74
| 2.4 High Energy Hall |  |  |  | 336.31 |  |  |  |  | 0 |  | 0 | 336.31 | 77.61
|  | 2.4.1 High Energy Hall |  |  |  |  | 336.31 |  |  | 0 |  | 0 | 336.31
|  |  | 2.4.1.1 EDI |  |  |  |  | 59.7 |  | 0 |  | 0 | 59.7
|  |  | 2.4.1.2 B&H |  |  |  |  | 199 |  | 0 |  | 0 | 199
|  |  | 2.4.1.3 Contingency |  |  |  |  | 77.61 |  | 0 |  | 0 | 77.61
| 2.5 Utilities and Services |  |  |  | 338.338 |  |  |  |  | 0 |  | 0 | 338.338 | 78.078
|  | 2.5.1 Electric Power Distribution |  |  |  |  | 157.17 |  |  | 0 |  | 0 | 157.17
|  |  | 2.5.1.1 EDI |  |  |  |  | 27.9 |  | 0 |  | 0 | 27.9
|  |  | 2.5.1.2 B&H |  |  |  |  | 93 |  | 0 |  | 0 | 93
|  |  | 2.5.1.3 Contingency |  |  |  |  | 36.27 |  | 0 |  | 0 | 36.27
|  | 2.5.2 Water, HP Air, Fire Suppression Distribution |  |  |  |  | 130.468 |  |  | 0 |  | 0 | 130.468
|  |  | 2.5.2.1 EDI |  |  |  |  | 23.16 |  | 0 |  | 0 | 23.16
|  |  | 2.5.2.2 B&H |  |  |  |  | 77.2 |  | 0 |  | 0 | 77.2
|  |  | 2.5.2.2.1 Water | [5 empty] | 52.2
|  |  | 2.5.2.2.2 High Pressure Air | [5 empty] | 11.9
|  |  | 2.5.2.2.3 Fire Suppression | [5 empty] | 13.1
|  |  | 2.5.2.3 Contingency |  |  |  |  | 30.108 |  | 0 |  | 0 | 30.108
|  | 2.5.3 Access and Penetrations |  |  |  |  | 50.7 |  |  | 0 |  | 0 | 50.7
|  |  | 2.5.3.1 EDI |  |  |  |  | 9 |  | 0 |  | 0 | 9
|  |  | 2.5.3.2 B&H |  |  |  |  | 30 |  | 0 |  | 0 | 30
|  |  | 2.5.3.3 Contingency |  |  |  |  | 11.7 |  | 0 |  | 0 | 11.7
| 2.6 Experimental Support Area |  |  |  | 0 |  |  |  |  | Concept is inadequate for cost estimate
|  | 2.6.1 Data Acquisition Room |  |  |  |  | 0
|  |  | 2.6.1.1 EDI |  |  |  |  | 0
|  |  | 2.6.1.2 B&H |  |  |  |  | 0
2.6.1.3 Contingency
|  | 2.6.2 Clean Room |  |  |  |  | 0
|  |  | 2.6.2.1 EDI |  |  |  |  | 0
|  |  | 2.6.2.2 B&H |  |  |  |  | 0
2.6.2.3 Contingency
|  | 2.6.3 User Rooms |  |  |  |  | 0
|  |  | 2.6.3.1 EDI |  |  |  |  | 0
|  |  | 2.6.3.2 B&H |  |  |  |  | 0
2.6.3.3 Contingency
|  | 2.6.4 Technician Rooms |  |  |  |  | 0
|  |  | 2.6.4.1 EDI |  |  |  |  | 0
|  |  | 2.6.4.2 B&H |  |  |  |  | 0
2.6.4.3 Contingency
|  | 2.6.5 Assembly and High Bay |  |  |  |  | 0
|  |  | 2.6.5.1 EDI |  |  |  |  | 0
|  |  | 2.6.5.2 B&H |  |  |  |  | 0
2.6.5.3 Contingency
3 Management |  |  |  | 1346.6629 | [5 empty] | 214.4752 |  | 0 | 1132.1877 | 49.4943
| 3.1 Project Office |  |  |  | 214.4752 |  |  |  |  | 214.4752 |  | 0 | 0 | 49.4943
|  | 3.1.1 ARDB Project Office |  |  |  |  | 214.4752 |  |  | 214.4752 |  | 0 | 0
|  |  | 3.1.1.1 ARDB Labor (2652 h) |  |  |  |  | 164.9809 |  | 164.9809 |  | 0 | 0
|  |  | 3.1.1.2 Contingency |  |  |  |  | 49.4943 |  | 49.4943 |  | 0 | 0
| 3.2 Project Support |  |  |  | 1132.1877 |  |  |  |  | 0 |  | 0 | 1132.1877
|  | 3.2.1 SLAC Indirect Charges |  |  |  |  | 1132.1877 |  |  | 0 |  | 0 | 1132.1877
|  |  | 3.2.1.1 Indirect Charges |  |  |  |  | 1132.1877 |  | 0 |  | 0 | 1132.1877
Indirect Charges Calculation:
On conventional accelerator project, ratio of M&S to Labor is 2:1.
Estimate of SLAC indirect charge is then
[(2 x M&S Ind. rate+ Labor Ind. Rate)/3] x Total New Technical Budget
At SLAC, M&S Ind. rate = 10% and Labor Ind. rate = 35%.
Weighted Indirect rate is 18%.