## Tasks
Task_ID | Task | Topic | Speciality | Description | Begin | Due | Contributors
1 | Experimental tests of compact optics | Beam Tests | Accelerator Physics | FF tests – at ATF / CLIC-3 / SLAC-line A/B | 2005-09-01 | TDR | with KEK, UK, SLAC, CERN participation
2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability | Beam Tests | Experimental Physics |  | Now | CDR | PEP-II, KEK-B, ATF, UK ???
3 | Experimental verification of backscattered photons in multi-bunch accelerator environment | Beam Tests | Experimental Physics |  | Now | TDR | LLNL
4 | Experimental verification of photon-photon collisions | Beam Tests | Experimental Physics |  | Now | TDR | LLNL
5 | Collimator material damage tests | Beam Tests | Experimental Physics |  | Now | TDR | SLAC
6 | Collimator wakefield tests | Beam Tests | Experimental Physics |  | Now | TDR | SLAC, UK
7 | BPM tests in IR-like environment | Beam Tests | Experimental Physics | ESA beam tests within 2-3 years from now | 2 years | TDR
8 | Pair monitor prototype beam test in ESA | Beam Tests | Experimental Physics |  | 2 years | TDR
9 | Prototype IR in ESA | Beam Tests | Experimental Physics | at SLAC/ESA? By SLAC, UK ? | CDR | TDR
10 | BPM tests at ESA and ATF | Beam Tests | Experimental Physics |  | CDR | TDR
11 | Develop “disrupted” and “pairs” beam capability at ESA | Beam Tests | Experimental Physics |  | 1 year | CDR
12 | EMI Test of VXD and Detector electronics | Beam Tests | Experimental Physics
13 | Collimation Study | Collimation & Bkgnds | Accelerator Physics | MARS, STRUCT, GEANT, other | Now | CDR | SLAC, FNAL, BNL, UK, Orsay, Saclay, KEK
14 | Tail-folding study | Collimation & Bkgnds | Accelerator Physics |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
15 | Collimation system performance study | Collimation & Bkgnds | Accelerator Physics | MARS, STRUCT, GEANT, other | Now | CDR | SLAC, FNAL, BNL, UK, Orsay, Saclay, KEK
16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle | Collimation & Bkgnds | Accelerator Physics | MARS, STRUCT, other |  |  | SLAC, FNAL, BNL, UK, Orsay, Saclay, KEK
17 | Muon backgrounds | Collimation & Bkgnds | HEP Simulation | Re-evaluate need for muon shielding in ILC context considering detector and PPS issues using MuCarlo, MARS, Struct, GEANT, other | Now | CDR | SLAC, FNAL, BNL, UK, Orsay, Saclay, KEK
18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme | Collimation & Bkgnds | HEP Simulation | MARS, STRUCT, GEANT, other | Now | CDR | SLAC, FNAL, BNL, UK, Orsay, Saclay, KEK
19 | Septum damage and background studies | Collimation & Bkgnds | HEP Simulation | MARS, STRUCT, GEANT, other | Now | CDR | SLAC, FNAL, BNL, UK, Orsay, Saclay, KEK
20 | Detector background analyses: Core Beam, Halo & SR | Collimation & Bkgnds | HEP Simulation | Improved studies of QSR or direct beam loss when LC is operating in non-optimal mode; Study backscattered QSR and its effect on feedback BPM; Placement of compton IP at start of Energy collimation region & tracking of off energy electrons | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized | Collimation & Bkgnds | HEP Simulation | Pairs, beam gas, neutrons, SR using MARS, STRUCT, GEANT, other |  |  | SLAC, FNAL, BNL, UK, Orsay, Saclay, KEK
22 | Study of engineering layouts and conflicts | Engineering | Civil Engineering |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer) | Engineering | Experimental Physics |  | CDR | TDR | UK
24 | Collimator material damage analysis | Engineering | HEP Simulation | EGS, FLUKA, GEANT, MARS, STRUCT, other | Now | CDR | SLAC, FNAL, BNL, UK, Orsay, Saclay, KEK
25 | Prototype collimators-exotic | Engineering | Mechanical Engineering |  | Now | TDR | SLAC, CERN
26 | Prototype collimators-traditional | Engineering | Mechanical Engineering |  | Now | TDR
27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets | Engineering | Mechanical Engineering | KEK support tube R&D program, FONT/FEATHER, Inertial Stabilization, Optical Stabilization; None of these needed in baseline model
28 | Engineering design & prototype BDS (not IR) quad supports and movers | Engineering | Mechanical Engineering |  | Now | TDR | SLAC, UK
29 | Document lengths, part counts, power requirements for working BDIR model | Engineering | System Engineering | Required for communication with Technical Support Groups (CF, ME, EE) | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
30 | Engineering study of compact SC quad | Final Doublet | Magnet Engineering |  | Now | CDR | BNL
31 | Prototype of compact SC quad | Final Doublet | Magnet Engineering |  | Now | CDR | BNL
32 | Engineering study of compact PM quad | Final Doublet | Magnet Engineering |  | Now | CDR | KEK, Kyoto
33 | Prototype of compact PM quad | Final Doublet | Magnet Engineering |  | Now | TDR | KEK, Kyoto
34 | Engineering study of large aperture traditional SC quad | Final Doublet | Magnet Engineering |  | Now | CDR | Orsay, Saclay, DESY
35 | Prototype of large aperture traditional SC quad | Final Doublet | Magnet Engineering |  | Now | TDR | Orsay, Saclay, DESY
36 | Study of gamma-gamma backgrounds vs. crossing angle | Gamma-Gamma | HEP Simulation |  | Now | CDR | LLNL
37 | Mechanical design of optical cavity for g-g laser | Gamma-Gamma | Optical Engineering |  | Now | CDR | LLNL
38 | Experimental test of g-g drive laser | Gamma-Gamma | Optical Engineering |  | Now | TDR | LLNL
39 | Experimental test of g-g mirror stability, damage | Gamma-Gamma | Optical Engineering |  | Now | TDR | LLNL
40 | Experimental test of g-g optical cavity | Gamma-Gamma | Optical Engineering |  | Now | TDR | LLNL
41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams | Instrumentation | Accelerator Physics | Proposal by Valery Telnov - Aims are the same as for the upstream spectrometer - The feasibility of precise position measurements at large distances for absolute calibration needs to be spelled out - Combining with polarimetry, both up- and downstream should be studied
42 | Track relative changes in energy distribution by measuring the spent beam | Instrumentation | Accelerator Physics | Use existing bends and plan mechanical or laser wires for beam size measurements - Initial study by Nick Walker - Needs to be taken up, presumably in connection with task number 3 (extraction line optical design)
43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer | Instrumentation | Electronic Engineering | 0.1 mm resolution - 5 10^(-5) precision | ? | TDR | SLAC, DESY
44 | Develop & prototype & beam test large aperture BPMs for BDS | Instrumentation | Electronic Engineering |  | ? | TDR | SLAC, DESY
45 | Laser wire prototypes & tests | Instrumentation | Experimental Physics |  | Now | TDR | KEK, UK
46 | Develop & prototype & beam test BPMs for IR | Instrumentation | Experimental Physics |  | ASAP | TDR | SLAC, DESY
47 | Develop next generation nanometer scale beam size monitor | Instrumentation | Experimental Physics |  | ATP | Commissioning | KEK
48 | Develop conceptual plan for post-IP energy spectrometer | Instrumentation | Experimental Physics | Specify magnets and detectors required
49 | Laser wire design, prototypes & tests | Instrumentation | Experimental Physics | Beam profile measurement with 4-5 mm resolution |  |  | G. Blair
50 | SLC style wire scanner design, prototypes, & test | Instrumentation | Experimental Physics | Beam profile measurement with 4-5 mm resolution
51 | Shintake laser interferometer design, prototypes & tests | Instrumentation | Experimental Physics
52 | Conceptual design of Pre-IP and Post-IP compton polarimeters | Instrumentation | Experimental Physics |  |  |  | P. Schüler
53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size | Instrumentation | RF Engineering | Precision required ? - Precision achieved in tests ?
54 | Beam position monitors based on cavity | Instrumentation | RF Engineering | Most stringent precision requirement, of about ~ 0.1 um, is from the upstream spectrometer - Elsewhere in the BDS requirements are ~ 1um - To be tested in beam environment, with high SR |  |  | J. Schreiber
55 | Beam position monitors based on stripline and on cavity | Instrumentation | RF Engineering | In final doublet for beam-beam deflections - Precision ~ 5 um ? - To be tested in beam environment, with high SR
56 | Study of tuning techniques | IP Collision Optimization | Accelerator Physics |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
57 | Study effect of S-shaped bunches on Luminosity stabilization | IP Collision Optimization | Accelerator Physics |  | Now | CDR
58 | Study of integrated feedback system performance | IP Collision Optimization | Accelerator Physics | Specify tolerances for vibration as function of frequency given baseline performance of bunch-bunch and train-train feedback and decide if any other vibration suppression or feedback systems (support tube, FONT/FEATHER, inertial stabilization, optical anchor) are required to reduce risk that tolerances not met | Now | CDR
59 | Feasibility study of RF cavity for angle feedback | IP Collision Optimization | Accelerator Physics |  | ASAP | CDR
60 | Luminosity diagnostic study | IP Collision Optimization | Accelerator Physics | Identify diagnostics for measuring and optimizing beam parameters | Now | CDR
61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts | IP Collision Optimization | Accelerator Physics | Fast + slow feedback to maintain optimal steering and optical tuning on the relevant time-scales - Trajectory feedback at IP with “realistic” beams has been simulated - Extraction of steering misalignements and beam optical parameters using the LCAL has also been studied (see previous task) |  |  | G. White
62 | Experimental measurements of quad stability in linac cryostat | IP Collision Optimization | Experimental Physics | Urgently needed as design optimization of the major linac component | ASAP | CDR | BNL
63 | Experimental measurements of cold mass stability in SC Final Quad | IP Collision Optimization | Experimental Physics |  | Now | TDR | BNL
64 | Study utility/location of a Shintake style laser interferometer | IP Collision Optimization | Experimental Physics
65 | Pair monitor performance study and conceptual design | IP Collision Optimization | HEP Simulation | Beam parameter vs Observables as a function of beam shape, crossing angle, conceptual design of detector, algorithm (extension of A.Stahl analysis) | Now | TDR
66 | L* Study | IR Layout | Accelerator Physics | Study tolerances and luminosity performance as a function of L* | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
67 | Crab cavity prototype tests of phase control and stability | IR Layout | Experimental Physics |  | Now | CDR | UK, FNAL?
68 | Agree on working model (Strawman) for IR Layout for both IRs | IR Layout | Experimental Physics | Suggest TESLA 0mrad model and NLC 20-mrad models as strawmen | Now | ASAP | SLAC, BNL, UK, Orsay, Saclay, KEK
69 | Conceptual IR Engineering design | IR Layout | Experimental Physics | These to include quad support with alignment and in situ adjustments; cable access; detector access; vacuum scheme, etc. | Now | CDR | SLAC, UK, DESY
70 | Detailed IR Engineering design | IR Layout | Mechanical Engineering |  | CDR | TDR
71 | Agree on working BDIR model | Optics | Accelerator Physics | These should be logically complete: 2 IRs, FEXT lines, all Beam Dumps, Pre-IP E & Pol, post-IP E & Pol. if allowed | Now | ASAP | SLAC, BNL, UK, Orsay, Saclay, KEK
72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model | Optics | Accelerator Physics |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
73 | Extraction Line Design | Optics | Accelerator Physics | Adequate bandwidth and optical properties appropriate for post-IP polarization and energy measurement; L*(ext) optimization; apertures; solenoid compensation if required | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
74 | Solenoid compensation study | Optics | Accelerator Physics |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs | Optics | Accelerator Physics |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
76 | Design of final doublet or quadruplet | Optics | Accelerator Physics |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
77 | Study of final focus philosophy | Optics | Accelerator Physics | Decide between traditional optics or that with local correction | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
78 | Study of multi-TeV upgrade modifications | Optics | Accelerator Physics |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
79 | Study effect of wakefields in BDS | Optics | Accelerator Physics |  | Now | TDR
80 | Design of Optically matched spin rotators in RTL sections | Optics | Accelerator Physics
81 | Conceptual Beam Dump engineering design | Optics | Mechanical Engineering | Where do the dumps go? TESLA model; US Options model? | Now | CDR
82 | Impact of apertures on SUSY | Simulations | Experimental Physics |  | Now | CDR | SLAC, BNL, UK, Orsay, Saclay, KEK
83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1 | Simulations | Experimental Physics
84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy | Simulations | Experimental Physics | Understand precision, detector requirements for reconstructing the average cms energy, the width of the core of the distribution and the event fraction in lower tail
85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g] | Simulations | Experimental Physics | Under study in several places - Statistics limited if only muons are used. Can ee, tt and qq be used ? Systematics evaluation
86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events | Simulations | Experimental Physics
87 | Define energy measurement scenario using the complementary information from beam and physics measurements | Simulations | Experimental Physics |  |  |  | D. Miller
88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad) | Simulations | Experimental Physics | Design under study by collaboration led by DESY-Zeuthen - Energy resolution ~ 10 % stochastic and ~ 1 % constant term - Specify accuracy requirement for absolute measurement (base-line HE machine versus GigaZ option) and study implications - Impact of a crossing angle |  |  | A. Stahl
89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad) | Simulations | Experimental Physics | Design under study by collaboration led by DESY-Zeuthen - Relative accuracy 1 % in 30-50 ns -> input to luminosity feedback loop - Optimise electron identification (and, separately) veto capabilities in the presence of pair and other radiation background from the beam-beam interaction - Impact of a crossing angle |  |  | A. Stahl
90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information | Simulations | Experimental Physics | Works without e+ polarisation - Absolute precision wrt collected luminosity ? Early study by Klaus Mönig and later by François Richard - Full analysis needed to get real estimate on precision ?
91 | BeamCal performance study and conceptual design | Simulations | HEP Simulation | Electron ID in 5-30mrad forward calorimeter; Improved e- ID algorithm | Now | TDR

## Choices
Choice_ID | Choice | Choice_Description
1 | Crossing Angle-(IR1/IR2)
2 | Final Doublet Technology (IR1/IR2)
3 | L* (IR1/IR2)
4 | Detector VXD inner radius (IR1/IR2)
5 | Collimation Choices (both Irs) | Collimation material & shape, Passive or Conumable, Order of betatron-energy collimation, collimation before/after IP switch
6 | MPS Questions | #bunches allowed to hit collimator
7 | Beam Stabilization issues | Yes/No: Rely on fast feedback solely; Yes/No: Additional active correction of FD; Yes/No: Additional fast feedback at BDS entrance; Yes/No: Additional fast feedbacks along the linac; Yes/No: Support tube across IP
8 | Detector Questions | Impact of EMI, gamma-gamma implications
9 | Instrumentation Choices
10 | Risk Mitigation | Beam Tests

## Choice-Task List
Choice_ID | Choice | Task_ID | Task
1 | Crossing Angle-(IR1/IR2) | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
1 | Crossing Angle-(IR1/IR2) | 7 | BPM tests in IR-like environment
1 | Crossing Angle-(IR1/IR2) | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
1 | Crossing Angle-(IR1/IR2) | 19 | Septum damage and background studies
1 | Crossing Angle-(IR1/IR2) | 20 | Detector background analyses: Core Beam, Halo & SR
1 | Crossing Angle-(IR1/IR2) | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
1 | Crossing Angle-(IR1/IR2) | 22 | Study of engineering layouts and conflicts
1 | Crossing Angle-(IR1/IR2) | 30 | Engineering study of compact SC quad
1 | Crossing Angle-(IR1/IR2) | 31 | Prototype of compact SC quad
1 | Crossing Angle-(IR1/IR2) | 32 | Engineering study of compact PM quad
1 | Crossing Angle-(IR1/IR2) | 33 | Prototype of compact PM quad
1 | Crossing Angle-(IR1/IR2) | 34 | Engineering study of large aperture traditional SC quad
1 | Crossing Angle-(IR1/IR2) | 35 | Prototype of large aperture traditional SC quad
1 | Crossing Angle-(IR1/IR2) | 36 | Study of gamma-gamma backgrounds vs. crossing angle
1 | Crossing Angle-(IR1/IR2) | 42 | Track relative changes in energy distribution by measuring the spent beam
1 | Crossing Angle-(IR1/IR2) | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
1 | Crossing Angle-(IR1/IR2) | 66 | L* Study
1 | Crossing Angle-(IR1/IR2) | 67 | Crab cavity prototype tests of phase control and stability
1 | Crossing Angle-(IR1/IR2) | 68 | Agree on working model (Strawman) for IR Layout for both IRs
1 | Crossing Angle-(IR1/IR2) | 69 | Conceptual IR Engineering design
1 | Crossing Angle-(IR1/IR2) | 70 | Detailed IR Engineering design
1 | Crossing Angle-(IR1/IR2) | 74 | Solenoid compensation study
1 | Crossing Angle-(IR1/IR2) | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
1 | Crossing Angle-(IR1/IR2) | 76 | Design of final doublet or quadruplet
1 | Crossing Angle-(IR1/IR2) | 81 | Conceptual Beam Dump engineering design
1 | Crossing Angle-(IR1/IR2) | 82 | Impact of apertures on SUSY
2 | Final Doublet Technology (IR1/IR2) | 9 | Prototype IR in ESA
2 | Final Doublet Technology (IR1/IR2) | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
2 | Final Doublet Technology (IR1/IR2) | 19 | Septum damage and background studies
2 | Final Doublet Technology (IR1/IR2) | 20 | Detector background analyses: Core Beam, Halo & SR
2 | Final Doublet Technology (IR1/IR2) | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
2 | Final Doublet Technology (IR1/IR2) | 22 | Study of engineering layouts and conflicts
2 | Final Doublet Technology (IR1/IR2) | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
2 | Final Doublet Technology (IR1/IR2) | 30 | Engineering study of compact SC quad
2 | Final Doublet Technology (IR1/IR2) | 31 | Prototype of compact SC quad
2 | Final Doublet Technology (IR1/IR2) | 32 | Engineering study of compact PM quad
2 | Final Doublet Technology (IR1/IR2) | 33 | Prototype of compact PM quad
2 | Final Doublet Technology (IR1/IR2) | 34 | Engineering study of large aperture traditional SC quad
2 | Final Doublet Technology (IR1/IR2) | 35 | Prototype of large aperture traditional SC quad
2 | Final Doublet Technology (IR1/IR2) | 58 | Study of integrated feedback system performance
2 | Final Doublet Technology (IR1/IR2) | 62 | Experimental measurements of quad stability in linac cryostat
2 | Final Doublet Technology (IR1/IR2) | 63 | Experimental measurements of cold mass stability in SC Final Quad
2 | Final Doublet Technology (IR1/IR2) | 66 | L* Study
2 | Final Doublet Technology (IR1/IR2) | 67 | Crab cavity prototype tests of phase control and stability
2 | Final Doublet Technology (IR1/IR2) | 69 | Conceptual IR Engineering design
2 | Final Doublet Technology (IR1/IR2) | 70 | Detailed IR Engineering design
2 | Final Doublet Technology (IR1/IR2) | 73 | Extraction Line Design
2 | Final Doublet Technology (IR1/IR2) | 74 | Solenoid compensation study
2 | Final Doublet Technology (IR1/IR2) | 76 | Design of final doublet or quadruplet
2 | Final Doublet Technology (IR1/IR2) | 82 | Impact of apertures on SUSY
3 | L* (IR1/IR2) | 1 | Experimental tests of compact optics
3 | L* (IR1/IR2) | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
3 | L* (IR1/IR2) | 3 | Experimental verification of backscattered photons in multi-bunch accelerator environment
3 | L* (IR1/IR2) | 4 | Experimental verification of photon-photon collisions
3 | L* (IR1/IR2) | 5 | Collimator material damage tests
3 | L* (IR1/IR2) | 6 | Collimator wakefield tests
3 | L* (IR1/IR2) | 7 | BPM tests in IR-like environment
3 | L* (IR1/IR2) | 8 | Pair monitor prototype beam test in ESA
3 | L* (IR1/IR2) | 9 | Prototype IR in ESA
3 | L* (IR1/IR2) | 10 | BPM tests at ESA and ATF
3 | L* (IR1/IR2) | 11 | Develop “disrupted” and “pairs” beam capability at ESA
3 | L* (IR1/IR2) | 12 | EMI Test of VXD and Detector electronics
3 | L* (IR1/IR2) | 13 | Collimation Study
3 | L* (IR1/IR2) | 14 | Tail-folding study
3 | L* (IR1/IR2) | 15 | Collimation system performance study
3 | L* (IR1/IR2) | 16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle
3 | L* (IR1/IR2) | 17 | Muon backgrounds
3 | L* (IR1/IR2) | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
3 | L* (IR1/IR2) | 19 | Septum damage and background studies
3 | L* (IR1/IR2) | 20 | Detector background analyses: Core Beam, Halo & SR
3 | L* (IR1/IR2) | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
3 | L* (IR1/IR2) | 22 | Study of engineering layouts and conflicts
3 | L* (IR1/IR2) | 23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer)
3 | L* (IR1/IR2) | 24 | Collimator material damage analysis
3 | L* (IR1/IR2) | 25 | Prototype collimators-exotic
3 | L* (IR1/IR2) | 26 | Prototype collimators-traditional
3 | L* (IR1/IR2) | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
3 | L* (IR1/IR2) | 28 | Engineering design & prototype BDS (not IR) quad supports and movers
3 | L* (IR1/IR2) | 29 | Document lengths, part counts, power requirements for working BDIR model
3 | L* (IR1/IR2) | 30 | Engineering study of compact SC quad
3 | L* (IR1/IR2) | 31 | Prototype of compact SC quad
3 | L* (IR1/IR2) | 32 | Engineering study of compact PM quad
3 | L* (IR1/IR2) | 33 | Prototype of compact PM quad
3 | L* (IR1/IR2) | 34 | Engineering study of large aperture traditional SC quad
3 | L* (IR1/IR2) | 35 | Prototype of large aperture traditional SC quad
3 | L* (IR1/IR2) | 36 | Study of gamma-gamma backgrounds vs. crossing angle
3 | L* (IR1/IR2) | 37 | Mechanical design of optical cavity for g-g laser
3 | L* (IR1/IR2) | 38 | Experimental test of g-g drive laser
3 | L* (IR1/IR2) | 39 | Experimental test of g-g mirror stability, damage
3 | L* (IR1/IR2) | 40 | Experimental test of g-g optical cavity
3 | L* (IR1/IR2) | 41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams
3 | L* (IR1/IR2) | 42 | Track relative changes in energy distribution by measuring the spent beam
3 | L* (IR1/IR2) | 43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer
3 | L* (IR1/IR2) | 44 | Develop & prototype & beam test large aperture BPMs for BDS
3 | L* (IR1/IR2) | 45 | Laser wire prototypes & tests
3 | L* (IR1/IR2) | 46 | Develop & prototype & beam test BPMs for IR
3 | L* (IR1/IR2) | 47 | Develop next generation nanometer scale beam size monitor
3 | L* (IR1/IR2) | 48 | Develop conceptual plan for post-IP energy spectrometer
3 | L* (IR1/IR2) | 49 | Laser wire design, prototypes & tests
3 | L* (IR1/IR2) | 50 | SLC style wire scanner design, prototypes, & test
3 | L* (IR1/IR2) | 51 | Shintake laser interferometer design, prototypes & tests
3 | L* (IR1/IR2) | 52 | Conceptual design of Pre-IP and Post-IP compton polarimeters
3 | L* (IR1/IR2) | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
3 | L* (IR1/IR2) | 54 | Beam position monitors based on cavity
3 | L* (IR1/IR2) | 55 | Beam position monitors based on stripline and on cavity
3 | L* (IR1/IR2) | 56 | Study of tuning techniques
3 | L* (IR1/IR2) | 57 | Study effect of S-shaped bunches on Luminosity stabilization
3 | L* (IR1/IR2) | 58 | Study of integrated feedback system performance
3 | L* (IR1/IR2) | 59 | Feasibility study of RF cavity for angle feedback
3 | L* (IR1/IR2) | 60 | Luminosity diagnostic study
3 | L* (IR1/IR2) | 61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts
3 | L* (IR1/IR2) | 62 | Experimental measurements of quad stability in linac cryostat
3 | L* (IR1/IR2) | 63 | Experimental measurements of cold mass stability in SC Final Quad
3 | L* (IR1/IR2) | 64 | Study utility/location of a Shintake style laser interferometer
3 | L* (IR1/IR2) | 65 | Pair monitor performance study and conceptual design
3 | L* (IR1/IR2) | 66 | L* Study
3 | L* (IR1/IR2) | 67 | Crab cavity prototype tests of phase control and stability
3 | L* (IR1/IR2) | 68 | Agree on working model (Strawman) for IR Layout for both IRs
3 | L* (IR1/IR2) | 69 | Conceptual IR Engineering design
3 | L* (IR1/IR2) | 70 | Detailed IR Engineering design
3 | L* (IR1/IR2) | 71 | Agree on working BDIR model
3 | L* (IR1/IR2) | 72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model
3 | L* (IR1/IR2) | 73 | Extraction Line Design
3 | L* (IR1/IR2) | 74 | Solenoid compensation study
3 | L* (IR1/IR2) | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
3 | L* (IR1/IR2) | 76 | Design of final doublet or quadruplet
3 | L* (IR1/IR2) | 77 | Study of final focus philosophy
3 | L* (IR1/IR2) | 78 | Study of multi-TeV upgrade modifications
3 | L* (IR1/IR2) | 79 | Study effect of wakefields in BDS
3 | L* (IR1/IR2) | 80 | Design of Optically matched spin rotators in RTL sections
3 | L* (IR1/IR2) | 81 | Conceptual Beam Dump engineering design
3 | L* (IR1/IR2) | 82 | Impact of apertures on SUSY
3 | L* (IR1/IR2) | 83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1
3 | L* (IR1/IR2) | 84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy
3 | L* (IR1/IR2) | 85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g]
3 | L* (IR1/IR2) | 86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events
3 | L* (IR1/IR2) | 87 | Define energy measurement scenario using the complementary information from beam and physics measurements
3 | L* (IR1/IR2) | 88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad)
3 | L* (IR1/IR2) | 89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad)
3 | L* (IR1/IR2) | 90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information
3 | L* (IR1/IR2) | 91 | BeamCal performance study and conceptual design
4 | Detector VXD inner radius (IR1/IR2) | 1 | Experimental tests of compact optics
4 | Detector VXD inner radius (IR1/IR2) | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
4 | Detector VXD inner radius (IR1/IR2) | 3 | Experimental verification of backscattered photons in multi-bunch accelerator environment
4 | Detector VXD inner radius (IR1/IR2) | 4 | Experimental verification of photon-photon collisions
4 | Detector VXD inner radius (IR1/IR2) | 5 | Collimator material damage tests
4 | Detector VXD inner radius (IR1/IR2) | 6 | Collimator wakefield tests
4 | Detector VXD inner radius (IR1/IR2) | 7 | BPM tests in IR-like environment
4 | Detector VXD inner radius (IR1/IR2) | 8 | Pair monitor prototype beam test in ESA
4 | Detector VXD inner radius (IR1/IR2) | 9 | Prototype IR in ESA
4 | Detector VXD inner radius (IR1/IR2) | 10 | BPM tests at ESA and ATF
4 | Detector VXD inner radius (IR1/IR2) | 11 | Develop “disrupted” and “pairs” beam capability at ESA
4 | Detector VXD inner radius (IR1/IR2) | 12 | EMI Test of VXD and Detector electronics
4 | Detector VXD inner radius (IR1/IR2) | 13 | Collimation Study
4 | Detector VXD inner radius (IR1/IR2) | 14 | Tail-folding study
4 | Detector VXD inner radius (IR1/IR2) | 15 | Collimation system performance study
4 | Detector VXD inner radius (IR1/IR2) | 16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle
4 | Detector VXD inner radius (IR1/IR2) | 17 | Muon backgrounds
4 | Detector VXD inner radius (IR1/IR2) | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
4 | Detector VXD inner radius (IR1/IR2) | 19 | Septum damage and background studies
4 | Detector VXD inner radius (IR1/IR2) | 20 | Detector background analyses: Core Beam, Halo & SR
4 | Detector VXD inner radius (IR1/IR2) | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
4 | Detector VXD inner radius (IR1/IR2) | 22 | Study of engineering layouts and conflicts
4 | Detector VXD inner radius (IR1/IR2) | 23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer)
4 | Detector VXD inner radius (IR1/IR2) | 24 | Collimator material damage analysis
4 | Detector VXD inner radius (IR1/IR2) | 25 | Prototype collimators-exotic
4 | Detector VXD inner radius (IR1/IR2) | 26 | Prototype collimators-traditional
4 | Detector VXD inner radius (IR1/IR2) | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
4 | Detector VXD inner radius (IR1/IR2) | 28 | Engineering design & prototype BDS (not IR) quad supports and movers
4 | Detector VXD inner radius (IR1/IR2) | 29 | Document lengths, part counts, power requirements for working BDIR model
4 | Detector VXD inner radius (IR1/IR2) | 30 | Engineering study of compact SC quad
4 | Detector VXD inner radius (IR1/IR2) | 31 | Prototype of compact SC quad
4 | Detector VXD inner radius (IR1/IR2) | 32 | Engineering study of compact PM quad
4 | Detector VXD inner radius (IR1/IR2) | 33 | Prototype of compact PM quad
4 | Detector VXD inner radius (IR1/IR2) | 34 | Engineering study of large aperture traditional SC quad
4 | Detector VXD inner radius (IR1/IR2) | 35 | Prototype of large aperture traditional SC quad
4 | Detector VXD inner radius (IR1/IR2) | 36 | Study of gamma-gamma backgrounds vs. crossing angle
4 | Detector VXD inner radius (IR1/IR2) | 37 | Mechanical design of optical cavity for g-g laser
4 | Detector VXD inner radius (IR1/IR2) | 38 | Experimental test of g-g drive laser
4 | Detector VXD inner radius (IR1/IR2) | 39 | Experimental test of g-g mirror stability, damage
4 | Detector VXD inner radius (IR1/IR2) | 40 | Experimental test of g-g optical cavity
4 | Detector VXD inner radius (IR1/IR2) | 41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams
4 | Detector VXD inner radius (IR1/IR2) | 42 | Track relative changes in energy distribution by measuring the spent beam
4 | Detector VXD inner radius (IR1/IR2) | 43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer
4 | Detector VXD inner radius (IR1/IR2) | 44 | Develop & prototype & beam test large aperture BPMs for BDS
4 | Detector VXD inner radius (IR1/IR2) | 45 | Laser wire prototypes & tests
4 | Detector VXD inner radius (IR1/IR2) | 46 | Develop & prototype & beam test BPMs for IR
4 | Detector VXD inner radius (IR1/IR2) | 47 | Develop next generation nanometer scale beam size monitor
4 | Detector VXD inner radius (IR1/IR2) | 48 | Develop conceptual plan for post-IP energy spectrometer
4 | Detector VXD inner radius (IR1/IR2) | 49 | Laser wire design, prototypes & tests
4 | Detector VXD inner radius (IR1/IR2) | 50 | SLC style wire scanner design, prototypes, & test
4 | Detector VXD inner radius (IR1/IR2) | 51 | Shintake laser interferometer design, prototypes & tests
4 | Detector VXD inner radius (IR1/IR2) | 52 | Conceptual design of Pre-IP and Post-IP compton polarimeters
4 | Detector VXD inner radius (IR1/IR2) | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
4 | Detector VXD inner radius (IR1/IR2) | 54 | Beam position monitors based on cavity
4 | Detector VXD inner radius (IR1/IR2) | 55 | Beam position monitors based on stripline and on cavity
4 | Detector VXD inner radius (IR1/IR2) | 56 | Study of tuning techniques
4 | Detector VXD inner radius (IR1/IR2) | 57 | Study effect of S-shaped bunches on Luminosity stabilization
4 | Detector VXD inner radius (IR1/IR2) | 58 | Study of integrated feedback system performance
4 | Detector VXD inner radius (IR1/IR2) | 59 | Feasibility study of RF cavity for angle feedback
4 | Detector VXD inner radius (IR1/IR2) | 60 | Luminosity diagnostic study
4 | Detector VXD inner radius (IR1/IR2) | 61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts
4 | Detector VXD inner radius (IR1/IR2) | 62 | Experimental measurements of quad stability in linac cryostat
4 | Detector VXD inner radius (IR1/IR2) | 63 | Experimental measurements of cold mass stability in SC Final Quad
4 | Detector VXD inner radius (IR1/IR2) | 64 | Study utility/location of a Shintake style laser interferometer
4 | Detector VXD inner radius (IR1/IR2) | 65 | Pair monitor performance study and conceptual design
4 | Detector VXD inner radius (IR1/IR2) | 66 | L* Study
4 | Detector VXD inner radius (IR1/IR2) | 67 | Crab cavity prototype tests of phase control and stability
4 | Detector VXD inner radius (IR1/IR2) | 68 | Agree on working model (Strawman) for IR Layout for both IRs
4 | Detector VXD inner radius (IR1/IR2) | 69 | Conceptual IR Engineering design
4 | Detector VXD inner radius (IR1/IR2) | 70 | Detailed IR Engineering design
4 | Detector VXD inner radius (IR1/IR2) | 71 | Agree on working BDIR model
4 | Detector VXD inner radius (IR1/IR2) | 72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model
4 | Detector VXD inner radius (IR1/IR2) | 73 | Extraction Line Design
4 | Detector VXD inner radius (IR1/IR2) | 74 | Solenoid compensation study
4 | Detector VXD inner radius (IR1/IR2) | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
4 | Detector VXD inner radius (IR1/IR2) | 76 | Design of final doublet or quadruplet
4 | Detector VXD inner radius (IR1/IR2) | 77 | Study of final focus philosophy
4 | Detector VXD inner radius (IR1/IR2) | 78 | Study of multi-TeV upgrade modifications
4 | Detector VXD inner radius (IR1/IR2) | 79 | Study effect of wakefields in BDS
4 | Detector VXD inner radius (IR1/IR2) | 80 | Design of Optically matched spin rotators in RTL sections
4 | Detector VXD inner radius (IR1/IR2) | 81 | Conceptual Beam Dump engineering design
4 | Detector VXD inner radius (IR1/IR2) | 82 | Impact of apertures on SUSY
4 | Detector VXD inner radius (IR1/IR2) | 83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1
4 | Detector VXD inner radius (IR1/IR2) | 84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy
4 | Detector VXD inner radius (IR1/IR2) | 85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g]
4 | Detector VXD inner radius (IR1/IR2) | 86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events
4 | Detector VXD inner radius (IR1/IR2) | 87 | Define energy measurement scenario using the complementary information from beam and physics measurements
4 | Detector VXD inner radius (IR1/IR2) | 88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad)
4 | Detector VXD inner radius (IR1/IR2) | 89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad)
4 | Detector VXD inner radius (IR1/IR2) | 90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information
4 | Detector VXD inner radius (IR1/IR2) | 91 | BeamCal performance study and conceptual design
5 | Collimation Choices (both Irs) | 1 | Experimental tests of compact optics
5 | Collimation Choices (both Irs) | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
5 | Collimation Choices (both Irs) | 3 | Experimental verification of backscattered photons in multi-bunch accelerator environment
5 | Collimation Choices (both Irs) | 4 | Experimental verification of photon-photon collisions
5 | Collimation Choices (both Irs) | 5 | Collimator material damage tests
5 | Collimation Choices (both Irs) | 6 | Collimator wakefield tests
5 | Collimation Choices (both Irs) | 7 | BPM tests in IR-like environment
5 | Collimation Choices (both Irs) | 8 | Pair monitor prototype beam test in ESA
5 | Collimation Choices (both Irs) | 9 | Prototype IR in ESA
5 | Collimation Choices (both Irs) | 10 | BPM tests at ESA and ATF
5 | Collimation Choices (both Irs) | 11 | Develop “disrupted” and “pairs” beam capability at ESA
5 | Collimation Choices (both Irs) | 12 | EMI Test of VXD and Detector electronics
5 | Collimation Choices (both Irs) | 13 | Collimation Study
5 | Collimation Choices (both Irs) | 14 | Tail-folding study
5 | Collimation Choices (both Irs) | 15 | Collimation system performance study
5 | Collimation Choices (both Irs) | 16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle
5 | Collimation Choices (both Irs) | 17 | Muon backgrounds
5 | Collimation Choices (both Irs) | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
5 | Collimation Choices (both Irs) | 19 | Septum damage and background studies
5 | Collimation Choices (both Irs) | 20 | Detector background analyses: Core Beam, Halo & SR
5 | Collimation Choices (both Irs) | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
5 | Collimation Choices (both Irs) | 22 | Study of engineering layouts and conflicts
5 | Collimation Choices (both Irs) | 23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer)
5 | Collimation Choices (both Irs) | 24 | Collimator material damage analysis
5 | Collimation Choices (both Irs) | 25 | Prototype collimators-exotic
5 | Collimation Choices (both Irs) | 26 | Prototype collimators-traditional
5 | Collimation Choices (both Irs) | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
5 | Collimation Choices (both Irs) | 28 | Engineering design & prototype BDS (not IR) quad supports and movers
5 | Collimation Choices (both Irs) | 29 | Document lengths, part counts, power requirements for working BDIR model
5 | Collimation Choices (both Irs) | 30 | Engineering study of compact SC quad
5 | Collimation Choices (both Irs) | 31 | Prototype of compact SC quad
5 | Collimation Choices (both Irs) | 32 | Engineering study of compact PM quad
5 | Collimation Choices (both Irs) | 33 | Prototype of compact PM quad
5 | Collimation Choices (both Irs) | 34 | Engineering study of large aperture traditional SC quad
5 | Collimation Choices (both Irs) | 35 | Prototype of large aperture traditional SC quad
5 | Collimation Choices (both Irs) | 36 | Study of gamma-gamma backgrounds vs. crossing angle
5 | Collimation Choices (both Irs) | 37 | Mechanical design of optical cavity for g-g laser
5 | Collimation Choices (both Irs) | 38 | Experimental test of g-g drive laser
5 | Collimation Choices (both Irs) | 39 | Experimental test of g-g mirror stability, damage
5 | Collimation Choices (both Irs) | 40 | Experimental test of g-g optical cavity
5 | Collimation Choices (both Irs) | 41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams
5 | Collimation Choices (both Irs) | 42 | Track relative changes in energy distribution by measuring the spent beam
5 | Collimation Choices (both Irs) | 43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer
5 | Collimation Choices (both Irs) | 44 | Develop & prototype & beam test large aperture BPMs for BDS
5 | Collimation Choices (both Irs) | 45 | Laser wire prototypes & tests
5 | Collimation Choices (both Irs) | 46 | Develop & prototype & beam test BPMs for IR
5 | Collimation Choices (both Irs) | 47 | Develop next generation nanometer scale beam size monitor
5 | Collimation Choices (both Irs) | 48 | Develop conceptual plan for post-IP energy spectrometer
5 | Collimation Choices (both Irs) | 49 | Laser wire design, prototypes & tests
5 | Collimation Choices (both Irs) | 50 | SLC style wire scanner design, prototypes, & test
5 | Collimation Choices (both Irs) | 51 | Shintake laser interferometer design, prototypes & tests
5 | Collimation Choices (both Irs) | 52 | Conceptual design of Pre-IP and Post-IP compton polarimeters
5 | Collimation Choices (both Irs) | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
5 | Collimation Choices (both Irs) | 54 | Beam position monitors based on cavity
5 | Collimation Choices (both Irs) | 55 | Beam position monitors based on stripline and on cavity
5 | Collimation Choices (both Irs) | 56 | Study of tuning techniques
5 | Collimation Choices (both Irs) | 57 | Study effect of S-shaped bunches on Luminosity stabilization
5 | Collimation Choices (both Irs) | 58 | Study of integrated feedback system performance
5 | Collimation Choices (both Irs) | 59 | Feasibility study of RF cavity for angle feedback
5 | Collimation Choices (both Irs) | 60 | Luminosity diagnostic study
5 | Collimation Choices (both Irs) | 61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts
5 | Collimation Choices (both Irs) | 62 | Experimental measurements of quad stability in linac cryostat
5 | Collimation Choices (both Irs) | 63 | Experimental measurements of cold mass stability in SC Final Quad
5 | Collimation Choices (both Irs) | 64 | Study utility/location of a Shintake style laser interferometer
5 | Collimation Choices (both Irs) | 65 | Pair monitor performance study and conceptual design
5 | Collimation Choices (both Irs) | 66 | L* Study
5 | Collimation Choices (both Irs) | 67 | Crab cavity prototype tests of phase control and stability
5 | Collimation Choices (both Irs) | 68 | Agree on working model (Strawman) for IR Layout for both IRs
5 | Collimation Choices (both Irs) | 69 | Conceptual IR Engineering design
5 | Collimation Choices (both Irs) | 70 | Detailed IR Engineering design
5 | Collimation Choices (both Irs) | 71 | Agree on working BDIR model
5 | Collimation Choices (both Irs) | 72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model
5 | Collimation Choices (both Irs) | 73 | Extraction Line Design
5 | Collimation Choices (both Irs) | 74 | Solenoid compensation study
5 | Collimation Choices (both Irs) | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
5 | Collimation Choices (both Irs) | 76 | Design of final doublet or quadruplet
5 | Collimation Choices (both Irs) | 77 | Study of final focus philosophy
5 | Collimation Choices (both Irs) | 78 | Study of multi-TeV upgrade modifications
5 | Collimation Choices (both Irs) | 79 | Study effect of wakefields in BDS
5 | Collimation Choices (both Irs) | 80 | Design of Optically matched spin rotators in RTL sections
5 | Collimation Choices (both Irs) | 81 | Conceptual Beam Dump engineering design
5 | Collimation Choices (both Irs) | 82 | Impact of apertures on SUSY
5 | Collimation Choices (both Irs) | 83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1
5 | Collimation Choices (both Irs) | 84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy
5 | Collimation Choices (both Irs) | 85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g]
5 | Collimation Choices (both Irs) | 86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events
5 | Collimation Choices (both Irs) | 87 | Define energy measurement scenario using the complementary information from beam and physics measurements
5 | Collimation Choices (both Irs) | 88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad)
5 | Collimation Choices (both Irs) | 89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad)
5 | Collimation Choices (both Irs) | 90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information
5 | Collimation Choices (both Irs) | 91 | BeamCal performance study and conceptual design
6 | MPS Questions | 1 | Experimental tests of compact optics
6 | MPS Questions | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
6 | MPS Questions | 3 | Experimental verification of backscattered photons in multi-bunch accelerator environment
6 | MPS Questions | 4 | Experimental verification of photon-photon collisions
6 | MPS Questions | 5 | Collimator material damage tests
6 | MPS Questions | 6 | Collimator wakefield tests
6 | MPS Questions | 7 | BPM tests in IR-like environment
6 | MPS Questions | 8 | Pair monitor prototype beam test in ESA
6 | MPS Questions | 9 | Prototype IR in ESA
6 | MPS Questions | 10 | BPM tests at ESA and ATF
6 | MPS Questions | 11 | Develop “disrupted” and “pairs” beam capability at ESA
6 | MPS Questions | 12 | EMI Test of VXD and Detector electronics
6 | MPS Questions | 13 | Collimation Study
6 | MPS Questions | 14 | Tail-folding study
6 | MPS Questions | 15 | Collimation system performance study
6 | MPS Questions | 16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle
6 | MPS Questions | 17 | Muon backgrounds
6 | MPS Questions | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
6 | MPS Questions | 19 | Septum damage and background studies
6 | MPS Questions | 20 | Detector background analyses: Core Beam, Halo & SR
6 | MPS Questions | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
6 | MPS Questions | 22 | Study of engineering layouts and conflicts
6 | MPS Questions | 23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer)
6 | MPS Questions | 24 | Collimator material damage analysis
6 | MPS Questions | 25 | Prototype collimators-exotic
6 | MPS Questions | 26 | Prototype collimators-traditional
6 | MPS Questions | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
6 | MPS Questions | 28 | Engineering design & prototype BDS (not IR) quad supports and movers
6 | MPS Questions | 29 | Document lengths, part counts, power requirements for working BDIR model
6 | MPS Questions | 30 | Engineering study of compact SC quad
6 | MPS Questions | 31 | Prototype of compact SC quad
6 | MPS Questions | 32 | Engineering study of compact PM quad
6 | MPS Questions | 33 | Prototype of compact PM quad
6 | MPS Questions | 34 | Engineering study of large aperture traditional SC quad
6 | MPS Questions | 35 | Prototype of large aperture traditional SC quad
6 | MPS Questions | 36 | Study of gamma-gamma backgrounds vs. crossing angle
6 | MPS Questions | 37 | Mechanical design of optical cavity for g-g laser
6 | MPS Questions | 38 | Experimental test of g-g drive laser
6 | MPS Questions | 39 | Experimental test of g-g mirror stability, damage
6 | MPS Questions | 40 | Experimental test of g-g optical cavity
6 | MPS Questions | 41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams
6 | MPS Questions | 42 | Track relative changes in energy distribution by measuring the spent beam
6 | MPS Questions | 43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer
6 | MPS Questions | 44 | Develop & prototype & beam test large aperture BPMs for BDS
6 | MPS Questions | 45 | Laser wire prototypes & tests
6 | MPS Questions | 46 | Develop & prototype & beam test BPMs for IR
6 | MPS Questions | 47 | Develop next generation nanometer scale beam size monitor
6 | MPS Questions | 48 | Develop conceptual plan for post-IP energy spectrometer
6 | MPS Questions | 49 | Laser wire design, prototypes & tests
6 | MPS Questions | 50 | SLC style wire scanner design, prototypes, & test
6 | MPS Questions | 51 | Shintake laser interferometer design, prototypes & tests
6 | MPS Questions | 52 | Conceptual design of Pre-IP and Post-IP compton polarimeters
6 | MPS Questions | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
6 | MPS Questions | 54 | Beam position monitors based on cavity
6 | MPS Questions | 55 | Beam position monitors based on stripline and on cavity
6 | MPS Questions | 56 | Study of tuning techniques
6 | MPS Questions | 57 | Study effect of S-shaped bunches on Luminosity stabilization
6 | MPS Questions | 58 | Study of integrated feedback system performance
6 | MPS Questions | 59 | Feasibility study of RF cavity for angle feedback
6 | MPS Questions | 60 | Luminosity diagnostic study
6 | MPS Questions | 61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts
6 | MPS Questions | 62 | Experimental measurements of quad stability in linac cryostat
6 | MPS Questions | 63 | Experimental measurements of cold mass stability in SC Final Quad
6 | MPS Questions | 64 | Study utility/location of a Shintake style laser interferometer
6 | MPS Questions | 65 | Pair monitor performance study and conceptual design
6 | MPS Questions | 66 | L* Study
6 | MPS Questions | 67 | Crab cavity prototype tests of phase control and stability
6 | MPS Questions | 68 | Agree on working model (Strawman) for IR Layout for both IRs
6 | MPS Questions | 69 | Conceptual IR Engineering design
6 | MPS Questions | 70 | Detailed IR Engineering design
6 | MPS Questions | 71 | Agree on working BDIR model
6 | MPS Questions | 72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model
6 | MPS Questions | 73 | Extraction Line Design
6 | MPS Questions | 74 | Solenoid compensation study
6 | MPS Questions | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
6 | MPS Questions | 76 | Design of final doublet or quadruplet
6 | MPS Questions | 77 | Study of final focus philosophy
6 | MPS Questions | 78 | Study of multi-TeV upgrade modifications
6 | MPS Questions | 79 | Study effect of wakefields in BDS
6 | MPS Questions | 80 | Design of Optically matched spin rotators in RTL sections
6 | MPS Questions | 81 | Conceptual Beam Dump engineering design
6 | MPS Questions | 82 | Impact of apertures on SUSY
6 | MPS Questions | 83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1
6 | MPS Questions | 84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy
6 | MPS Questions | 85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g]
6 | MPS Questions | 86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events
6 | MPS Questions | 87 | Define energy measurement scenario using the complementary information from beam and physics measurements
6 | MPS Questions | 88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad)
6 | MPS Questions | 89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad)
6 | MPS Questions | 90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information
6 | MPS Questions | 91 | BeamCal performance study and conceptual design
7 | Beam Stabilization issues | 1 | Experimental tests of compact optics
7 | Beam Stabilization issues | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
7 | Beam Stabilization issues | 3 | Experimental verification of backscattered photons in multi-bunch accelerator environment
7 | Beam Stabilization issues | 4 | Experimental verification of photon-photon collisions
7 | Beam Stabilization issues | 5 | Collimator material damage tests
7 | Beam Stabilization issues | 6 | Collimator wakefield tests
7 | Beam Stabilization issues | 7 | BPM tests in IR-like environment
7 | Beam Stabilization issues | 8 | Pair monitor prototype beam test in ESA
7 | Beam Stabilization issues | 9 | Prototype IR in ESA
7 | Beam Stabilization issues | 10 | BPM tests at ESA and ATF
7 | Beam Stabilization issues | 11 | Develop “disrupted” and “pairs” beam capability at ESA
7 | Beam Stabilization issues | 12 | EMI Test of VXD and Detector electronics
7 | Beam Stabilization issues | 13 | Collimation Study
7 | Beam Stabilization issues | 14 | Tail-folding study
7 | Beam Stabilization issues | 15 | Collimation system performance study
7 | Beam Stabilization issues | 16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle
7 | Beam Stabilization issues | 17 | Muon backgrounds
7 | Beam Stabilization issues | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
7 | Beam Stabilization issues | 19 | Septum damage and background studies
7 | Beam Stabilization issues | 20 | Detector background analyses: Core Beam, Halo & SR
7 | Beam Stabilization issues | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
7 | Beam Stabilization issues | 22 | Study of engineering layouts and conflicts
7 | Beam Stabilization issues | 23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer)
7 | Beam Stabilization issues | 24 | Collimator material damage analysis
7 | Beam Stabilization issues | 25 | Prototype collimators-exotic
7 | Beam Stabilization issues | 26 | Prototype collimators-traditional
7 | Beam Stabilization issues | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
7 | Beam Stabilization issues | 28 | Engineering design & prototype BDS (not IR) quad supports and movers
7 | Beam Stabilization issues | 29 | Document lengths, part counts, power requirements for working BDIR model
7 | Beam Stabilization issues | 30 | Engineering study of compact SC quad
7 | Beam Stabilization issues | 31 | Prototype of compact SC quad
7 | Beam Stabilization issues | 32 | Engineering study of compact PM quad
7 | Beam Stabilization issues | 33 | Prototype of compact PM quad
7 | Beam Stabilization issues | 34 | Engineering study of large aperture traditional SC quad
7 | Beam Stabilization issues | 35 | Prototype of large aperture traditional SC quad
7 | Beam Stabilization issues | 36 | Study of gamma-gamma backgrounds vs. crossing angle
7 | Beam Stabilization issues | 37 | Mechanical design of optical cavity for g-g laser
7 | Beam Stabilization issues | 38 | Experimental test of g-g drive laser
7 | Beam Stabilization issues | 39 | Experimental test of g-g mirror stability, damage
7 | Beam Stabilization issues | 40 | Experimental test of g-g optical cavity
7 | Beam Stabilization issues | 41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams
7 | Beam Stabilization issues | 42 | Track relative changes in energy distribution by measuring the spent beam
7 | Beam Stabilization issues | 43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer
7 | Beam Stabilization issues | 44 | Develop & prototype & beam test large aperture BPMs for BDS
7 | Beam Stabilization issues | 45 | Laser wire prototypes & tests
7 | Beam Stabilization issues | 46 | Develop & prototype & beam test BPMs for IR
7 | Beam Stabilization issues | 47 | Develop next generation nanometer scale beam size monitor
7 | Beam Stabilization issues | 48 | Develop conceptual plan for post-IP energy spectrometer
7 | Beam Stabilization issues | 49 | Laser wire design, prototypes & tests
7 | Beam Stabilization issues | 50 | SLC style wire scanner design, prototypes, & test
7 | Beam Stabilization issues | 51 | Shintake laser interferometer design, prototypes & tests
7 | Beam Stabilization issues | 52 | Conceptual design of Pre-IP and Post-IP compton polarimeters
7 | Beam Stabilization issues | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
7 | Beam Stabilization issues | 54 | Beam position monitors based on cavity
7 | Beam Stabilization issues | 55 | Beam position monitors based on stripline and on cavity
7 | Beam Stabilization issues | 56 | Study of tuning techniques
7 | Beam Stabilization issues | 57 | Study effect of S-shaped bunches on Luminosity stabilization
7 | Beam Stabilization issues | 58 | Study of integrated feedback system performance
7 | Beam Stabilization issues | 59 | Feasibility study of RF cavity for angle feedback
7 | Beam Stabilization issues | 60 | Luminosity diagnostic study
7 | Beam Stabilization issues | 61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts
7 | Beam Stabilization issues | 62 | Experimental measurements of quad stability in linac cryostat
7 | Beam Stabilization issues | 63 | Experimental measurements of cold mass stability in SC Final Quad
7 | Beam Stabilization issues | 64 | Study utility/location of a Shintake style laser interferometer
7 | Beam Stabilization issues | 65 | Pair monitor performance study and conceptual design
7 | Beam Stabilization issues | 66 | L* Study
7 | Beam Stabilization issues | 67 | Crab cavity prototype tests of phase control and stability
7 | Beam Stabilization issues | 68 | Agree on working model (Strawman) for IR Layout for both IRs
7 | Beam Stabilization issues | 69 | Conceptual IR Engineering design
7 | Beam Stabilization issues | 70 | Detailed IR Engineering design
7 | Beam Stabilization issues | 71 | Agree on working BDIR model
7 | Beam Stabilization issues | 72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model
7 | Beam Stabilization issues | 73 | Extraction Line Design
7 | Beam Stabilization issues | 74 | Solenoid compensation study
7 | Beam Stabilization issues | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
7 | Beam Stabilization issues | 76 | Design of final doublet or quadruplet
7 | Beam Stabilization issues | 77 | Study of final focus philosophy
7 | Beam Stabilization issues | 78 | Study of multi-TeV upgrade modifications
7 | Beam Stabilization issues | 79 | Study effect of wakefields in BDS
7 | Beam Stabilization issues | 80 | Design of Optically matched spin rotators in RTL sections
7 | Beam Stabilization issues | 81 | Conceptual Beam Dump engineering design
7 | Beam Stabilization issues | 82 | Impact of apertures on SUSY
7 | Beam Stabilization issues | 83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1
7 | Beam Stabilization issues | 84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy
7 | Beam Stabilization issues | 85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g]
7 | Beam Stabilization issues | 86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events
7 | Beam Stabilization issues | 87 | Define energy measurement scenario using the complementary information from beam and physics measurements
7 | Beam Stabilization issues | 88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad)
7 | Beam Stabilization issues | 89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad)
7 | Beam Stabilization issues | 90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information
7 | Beam Stabilization issues | 91 | BeamCal performance study and conceptual design
8 | Detector Questions | 1 | Experimental tests of compact optics
8 | Detector Questions | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
8 | Detector Questions | 3 | Experimental verification of backscattered photons in multi-bunch accelerator environment
8 | Detector Questions | 4 | Experimental verification of photon-photon collisions
8 | Detector Questions | 5 | Collimator material damage tests
8 | Detector Questions | 6 | Collimator wakefield tests
8 | Detector Questions | 7 | BPM tests in IR-like environment
8 | Detector Questions | 8 | Pair monitor prototype beam test in ESA
8 | Detector Questions | 9 | Prototype IR in ESA
8 | Detector Questions | 10 | BPM tests at ESA and ATF
8 | Detector Questions | 11 | Develop “disrupted” and “pairs” beam capability at ESA
8 | Detector Questions | 12 | EMI Test of VXD and Detector electronics
8 | Detector Questions | 13 | Collimation Study
8 | Detector Questions | 14 | Tail-folding study
8 | Detector Questions | 15 | Collimation system performance study
8 | Detector Questions | 16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle
8 | Detector Questions | 17 | Muon backgrounds
8 | Detector Questions | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
8 | Detector Questions | 19 | Septum damage and background studies
8 | Detector Questions | 20 | Detector background analyses: Core Beam, Halo & SR
8 | Detector Questions | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
8 | Detector Questions | 22 | Study of engineering layouts and conflicts
8 | Detector Questions | 23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer)
8 | Detector Questions | 24 | Collimator material damage analysis
8 | Detector Questions | 25 | Prototype collimators-exotic
8 | Detector Questions | 26 | Prototype collimators-traditional
8 | Detector Questions | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
8 | Detector Questions | 28 | Engineering design & prototype BDS (not IR) quad supports and movers
8 | Detector Questions | 29 | Document lengths, part counts, power requirements for working BDIR model
8 | Detector Questions | 30 | Engineering study of compact SC quad
8 | Detector Questions | 31 | Prototype of compact SC quad
8 | Detector Questions | 32 | Engineering study of compact PM quad
8 | Detector Questions | 33 | Prototype of compact PM quad
8 | Detector Questions | 34 | Engineering study of large aperture traditional SC quad
8 | Detector Questions | 35 | Prototype of large aperture traditional SC quad
8 | Detector Questions | 36 | Study of gamma-gamma backgrounds vs. crossing angle
8 | Detector Questions | 37 | Mechanical design of optical cavity for g-g laser
8 | Detector Questions | 38 | Experimental test of g-g drive laser
8 | Detector Questions | 39 | Experimental test of g-g mirror stability, damage
8 | Detector Questions | 40 | Experimental test of g-g optical cavity
8 | Detector Questions | 41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams
8 | Detector Questions | 42 | Track relative changes in energy distribution by measuring the spent beam
8 | Detector Questions | 43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer
8 | Detector Questions | 44 | Develop & prototype & beam test large aperture BPMs for BDS
8 | Detector Questions | 45 | Laser wire prototypes & tests
8 | Detector Questions | 46 | Develop & prototype & beam test BPMs for IR
8 | Detector Questions | 47 | Develop next generation nanometer scale beam size monitor
8 | Detector Questions | 48 | Develop conceptual plan for post-IP energy spectrometer
8 | Detector Questions | 49 | Laser wire design, prototypes & tests
8 | Detector Questions | 50 | SLC style wire scanner design, prototypes, & test
8 | Detector Questions | 51 | Shintake laser interferometer design, prototypes & tests
8 | Detector Questions | 52 | Conceptual design of Pre-IP and Post-IP compton polarimeters
8 | Detector Questions | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
8 | Detector Questions | 54 | Beam position monitors based on cavity
8 | Detector Questions | 55 | Beam position monitors based on stripline and on cavity
8 | Detector Questions | 56 | Study of tuning techniques
8 | Detector Questions | 57 | Study effect of S-shaped bunches on Luminosity stabilization
8 | Detector Questions | 58 | Study of integrated feedback system performance
8 | Detector Questions | 59 | Feasibility study of RF cavity for angle feedback
8 | Detector Questions | 60 | Luminosity diagnostic study
8 | Detector Questions | 61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts
8 | Detector Questions | 62 | Experimental measurements of quad stability in linac cryostat
8 | Detector Questions | 63 | Experimental measurements of cold mass stability in SC Final Quad
8 | Detector Questions | 64 | Study utility/location of a Shintake style laser interferometer
8 | Detector Questions | 65 | Pair monitor performance study and conceptual design
8 | Detector Questions | 66 | L* Study
8 | Detector Questions | 67 | Crab cavity prototype tests of phase control and stability
8 | Detector Questions | 68 | Agree on working model (Strawman) for IR Layout for both IRs
8 | Detector Questions | 69 | Conceptual IR Engineering design
8 | Detector Questions | 70 | Detailed IR Engineering design
8 | Detector Questions | 71 | Agree on working BDIR model
8 | Detector Questions | 72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model
8 | Detector Questions | 73 | Extraction Line Design
8 | Detector Questions | 74 | Solenoid compensation study
8 | Detector Questions | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
8 | Detector Questions | 76 | Design of final doublet or quadruplet
8 | Detector Questions | 77 | Study of final focus philosophy
8 | Detector Questions | 78 | Study of multi-TeV upgrade modifications
8 | Detector Questions | 79 | Study effect of wakefields in BDS
8 | Detector Questions | 80 | Design of Optically matched spin rotators in RTL sections
8 | Detector Questions | 81 | Conceptual Beam Dump engineering design
8 | Detector Questions | 82 | Impact of apertures on SUSY
8 | Detector Questions | 83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1
8 | Detector Questions | 84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy
8 | Detector Questions | 85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g]
8 | Detector Questions | 86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events
8 | Detector Questions | 87 | Define energy measurement scenario using the complementary information from beam and physics measurements
8 | Detector Questions | 88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad)
8 | Detector Questions | 89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad)
8 | Detector Questions | 90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information
8 | Detector Questions | 91 | BeamCal performance study and conceptual design
9 | Instrumentation Choices | 1 | Experimental tests of compact optics
9 | Instrumentation Choices | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
9 | Instrumentation Choices | 3 | Experimental verification of backscattered photons in multi-bunch accelerator environment
9 | Instrumentation Choices | 4 | Experimental verification of photon-photon collisions
9 | Instrumentation Choices | 5 | Collimator material damage tests
9 | Instrumentation Choices | 6 | Collimator wakefield tests
9 | Instrumentation Choices | 7 | BPM tests in IR-like environment
9 | Instrumentation Choices | 8 | Pair monitor prototype beam test in ESA
9 | Instrumentation Choices | 9 | Prototype IR in ESA
9 | Instrumentation Choices | 10 | BPM tests at ESA and ATF
9 | Instrumentation Choices | 11 | Develop “disrupted” and “pairs” beam capability at ESA
9 | Instrumentation Choices | 12 | EMI Test of VXD and Detector electronics
9 | Instrumentation Choices | 13 | Collimation Study
9 | Instrumentation Choices | 14 | Tail-folding study
9 | Instrumentation Choices | 15 | Collimation system performance study
9 | Instrumentation Choices | 16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle
9 | Instrumentation Choices | 17 | Muon backgrounds
9 | Instrumentation Choices | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
9 | Instrumentation Choices | 19 | Septum damage and background studies
9 | Instrumentation Choices | 20 | Detector background analyses: Core Beam, Halo & SR
9 | Instrumentation Choices | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
9 | Instrumentation Choices | 22 | Study of engineering layouts and conflicts
9 | Instrumentation Choices | 23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer)
9 | Instrumentation Choices | 24 | Collimator material damage analysis
9 | Instrumentation Choices | 25 | Prototype collimators-exotic
9 | Instrumentation Choices | 26 | Prototype collimators-traditional
9 | Instrumentation Choices | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
9 | Instrumentation Choices | 28 | Engineering design & prototype BDS (not IR) quad supports and movers
9 | Instrumentation Choices | 29 | Document lengths, part counts, power requirements for working BDIR model
9 | Instrumentation Choices | 30 | Engineering study of compact SC quad
9 | Instrumentation Choices | 31 | Prototype of compact SC quad
9 | Instrumentation Choices | 32 | Engineering study of compact PM quad
9 | Instrumentation Choices | 33 | Prototype of compact PM quad
9 | Instrumentation Choices | 34 | Engineering study of large aperture traditional SC quad
9 | Instrumentation Choices | 35 | Prototype of large aperture traditional SC quad
9 | Instrumentation Choices | 36 | Study of gamma-gamma backgrounds vs. crossing angle
9 | Instrumentation Choices | 37 | Mechanical design of optical cavity for g-g laser
9 | Instrumentation Choices | 38 | Experimental test of g-g drive laser
9 | Instrumentation Choices | 39 | Experimental test of g-g mirror stability, damage
9 | Instrumentation Choices | 40 | Experimental test of g-g optical cavity
9 | Instrumentation Choices | 41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams
9 | Instrumentation Choices | 42 | Track relative changes in energy distribution by measuring the spent beam
9 | Instrumentation Choices | 43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer
9 | Instrumentation Choices | 44 | Develop & prototype & beam test large aperture BPMs for BDS
9 | Instrumentation Choices | 45 | Laser wire prototypes & tests
9 | Instrumentation Choices | 46 | Develop & prototype & beam test BPMs for IR
9 | Instrumentation Choices | 47 | Develop next generation nanometer scale beam size monitor
9 | Instrumentation Choices | 48 | Develop conceptual plan for post-IP energy spectrometer
9 | Instrumentation Choices | 49 | Laser wire design, prototypes & tests
9 | Instrumentation Choices | 50 | SLC style wire scanner design, prototypes, & test
9 | Instrumentation Choices | 51 | Shintake laser interferometer design, prototypes & tests
9 | Instrumentation Choices | 52 | Conceptual design of Pre-IP and Post-IP compton polarimeters
9 | Instrumentation Choices | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
9 | Instrumentation Choices | 54 | Beam position monitors based on cavity
9 | Instrumentation Choices | 55 | Beam position monitors based on stripline and on cavity
9 | Instrumentation Choices | 56 | Study of tuning techniques
9 | Instrumentation Choices | 57 | Study effect of S-shaped bunches on Luminosity stabilization
9 | Instrumentation Choices | 58 | Study of integrated feedback system performance
9 | Instrumentation Choices | 59 | Feasibility study of RF cavity for angle feedback
9 | Instrumentation Choices | 60 | Luminosity diagnostic study
9 | Instrumentation Choices | 61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts
9 | Instrumentation Choices | 62 | Experimental measurements of quad stability in linac cryostat
9 | Instrumentation Choices | 63 | Experimental measurements of cold mass stability in SC Final Quad
9 | Instrumentation Choices | 64 | Study utility/location of a Shintake style laser interferometer
9 | Instrumentation Choices | 65 | Pair monitor performance study and conceptual design
9 | Instrumentation Choices | 66 | L* Study
9 | Instrumentation Choices | 67 | Crab cavity prototype tests of phase control and stability
9 | Instrumentation Choices | 68 | Agree on working model (Strawman) for IR Layout for both IRs
9 | Instrumentation Choices | 69 | Conceptual IR Engineering design
9 | Instrumentation Choices | 70 | Detailed IR Engineering design
9 | Instrumentation Choices | 71 | Agree on working BDIR model
9 | Instrumentation Choices | 72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model
9 | Instrumentation Choices | 73 | Extraction Line Design
9 | Instrumentation Choices | 74 | Solenoid compensation study
9 | Instrumentation Choices | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
9 | Instrumentation Choices | 76 | Design of final doublet or quadruplet
9 | Instrumentation Choices | 77 | Study of final focus philosophy
9 | Instrumentation Choices | 78 | Study of multi-TeV upgrade modifications
9 | Instrumentation Choices | 79 | Study effect of wakefields in BDS
9 | Instrumentation Choices | 80 | Design of Optically matched spin rotators in RTL sections
9 | Instrumentation Choices | 81 | Conceptual Beam Dump engineering design
9 | Instrumentation Choices | 82 | Impact of apertures on SUSY
9 | Instrumentation Choices | 83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1
9 | Instrumentation Choices | 84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy
9 | Instrumentation Choices | 85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g]
9 | Instrumentation Choices | 86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events
9 | Instrumentation Choices | 87 | Define energy measurement scenario using the complementary information from beam and physics measurements
9 | Instrumentation Choices | 88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad)
9 | Instrumentation Choices | 89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad)
9 | Instrumentation Choices | 90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information
9 | Instrumentation Choices | 91 | BeamCal performance study and conceptual design
10 | Risk Mitigation | 1 | Experimental tests of compact optics
10 | Risk Mitigation | 2 | Electrostatic separator experimental tests in harsh environment, up to 500 GeV/beam, feasibility and reliability
10 | Risk Mitigation | 3 | Experimental verification of backscattered photons in multi-bunch accelerator environment
10 | Risk Mitigation | 4 | Experimental verification of photon-photon collisions
10 | Risk Mitigation | 5 | Collimator material damage tests
10 | Risk Mitigation | 6 | Collimator wakefield tests
10 | Risk Mitigation | 7 | BPM tests in IR-like environment
10 | Risk Mitigation | 8 | Pair monitor prototype beam test in ESA
10 | Risk Mitigation | 9 | Prototype IR in ESA
10 | Risk Mitigation | 10 | BPM tests at ESA and ATF
10 | Risk Mitigation | 11 | Develop “disrupted” and “pairs” beam capability at ESA
10 | Risk Mitigation | 12 | EMI Test of VXD and Detector electronics
10 | Risk Mitigation | 13 | Collimation Study
10 | Risk Mitigation | 14 | Tail-folding study
10 | Risk Mitigation | 15 | Collimation system performance study
10 | Risk Mitigation | 16 | Re-estimate of beam halo and decision on halo/beam fraction collimation system and shielding will be designed to handle
10 | Risk Mitigation | 17 | Muon backgrounds
10 | Risk Mitigation | 18 | Study backgrounds caused by main beam and halo as a function of crossing angle and extraction scheme
10 | Risk Mitigation | 19 | Septum damage and background studies
10 | Risk Mitigation | 20 | Detector background analyses: Core Beam, Halo & SR
10 | Risk Mitigation | 21 | Recalculation of all detector backgrounds once CDR version of IR Layouts are finalized
10 | Risk Mitigation | 22 | Study of engineering layouts and conflicts
10 | Risk Mitigation | 23 | Develop & prototype Interferometric network for specific areas (e.g. energy spectrometer)
10 | Risk Mitigation | 24 | Collimator material damage analysis
10 | Risk Mitigation | 25 | Prototype collimators-exotic
10 | Risk Mitigation | 26 | Prototype collimators-traditional
10 | Risk Mitigation | 27 | Engineering study/prototypes any auxiliary vibration suppression system that can substantially reduce risk due to relative vibration of magnets
10 | Risk Mitigation | 28 | Engineering design & prototype BDS (not IR) quad supports and movers
10 | Risk Mitigation | 29 | Document lengths, part counts, power requirements for working BDIR model
10 | Risk Mitigation | 30 | Engineering study of compact SC quad
10 | Risk Mitigation | 31 | Prototype of compact SC quad
10 | Risk Mitigation | 32 | Engineering study of compact PM quad
10 | Risk Mitigation | 33 | Prototype of compact PM quad
10 | Risk Mitigation | 34 | Engineering study of large aperture traditional SC quad
10 | Risk Mitigation | 35 | Prototype of large aperture traditional SC quad
10 | Risk Mitigation | 36 | Study of gamma-gamma backgrounds vs. crossing angle
10 | Risk Mitigation | 37 | Mechanical design of optical cavity for g-g laser
10 | Risk Mitigation | 38 | Experimental test of g-g drive laser
10 | Risk Mitigation | 39 | Experimental test of g-g mirror stability, damage
10 | Risk Mitigation | 40 | Experimental test of g-g optical cavity
10 | Risk Mitigation | 41 | Measurement of spin precession through existing bending magnets to extract the integrated bending field used is a spectrometre - The claim is that reduced requirements on BPMs result because larger bend angles and drifts can be used - A prerequisite of this method is polarisation of both beams
10 | Risk Mitigation | 42 | Track relative changes in energy distribution by measuring the spent beam
10 | Risk Mitigation | 43 | Develop & prototype & beam test cavity BPM for pre-IP energy spectrometer
10 | Risk Mitigation | 44 | Develop & prototype & beam test large aperture BPMs for BDS
10 | Risk Mitigation | 45 | Laser wire prototypes & tests
10 | Risk Mitigation | 46 | Develop & prototype & beam test BPMs for IR
10 | Risk Mitigation | 47 | Develop next generation nanometer scale beam size monitor
10 | Risk Mitigation | 48 | Develop conceptual plan for post-IP energy spectrometer
10 | Risk Mitigation | 49 | Laser wire design, prototypes & tests
10 | Risk Mitigation | 50 | SLC style wire scanner design, prototypes, & test
10 | Risk Mitigation | 51 | Shintake laser interferometer design, prototypes & tests
10 | Risk Mitigation | 52 | Conceptual design of Pre-IP and Post-IP compton polarimeters
10 | Risk Mitigation | 53 | Design, prototypes & tests of a RF cavity to provide time-dependent kick allowing to extract bunch length from transverse size
10 | Risk Mitigation | 54 | Beam position monitors based on cavity
10 | Risk Mitigation | 55 | Beam position monitors based on stripline and on cavity
10 | Risk Mitigation | 56 | Study of tuning techniques
10 | Risk Mitigation | 57 | Study effect of S-shaped bunches on Luminosity stabilization
10 | Risk Mitigation | 58 | Study of integrated feedback system performance
10 | Risk Mitigation | 59 | Feasibility study of RF cavity for angle feedback
10 | Risk Mitigation | 60 | Luminosity diagnostic study
10 | Risk Mitigation | 61 | Optimize LUM by using beam-beam deflections, pairs and BDS trajectory measuremnts
10 | Risk Mitigation | 62 | Experimental measurements of quad stability in linac cryostat
10 | Risk Mitigation | 63 | Experimental measurements of cold mass stability in SC Final Quad
10 | Risk Mitigation | 64 | Study utility/location of a Shintake style laser interferometer
10 | Risk Mitigation | 65 | Pair monitor performance study and conceptual design
10 | Risk Mitigation | 66 | L* Study
10 | Risk Mitigation | 67 | Crab cavity prototype tests of phase control and stability
10 | Risk Mitigation | 68 | Agree on working model (Strawman) for IR Layout for both IRs
10 | Risk Mitigation | 69 | Conceptual IR Engineering design
10 | Risk Mitigation | 70 | Detailed IR Engineering design
10 | Risk Mitigation | 71 | Agree on working BDIR model
10 | Risk Mitigation | 72 | Assemble and release internally consistent set of BDIR decks describing working BDIR model
10 | Risk Mitigation | 73 | Extraction Line Design
10 | Risk Mitigation | 74 | Solenoid compensation study
10 | Risk Mitigation | 75 | Study of impact of last drift space before detector required for zero or very small crossing angle designs
10 | Risk Mitigation | 76 | Design of final doublet or quadruplet
10 | Risk Mitigation | 77 | Study of final focus philosophy
10 | Risk Mitigation | 78 | Study of multi-TeV upgrade modifications
10 | Risk Mitigation | 79 | Study effect of wakefields in BDS
10 | Risk Mitigation | 80 | Design of Optically matched spin rotators in RTL sections
10 | Risk Mitigation | 81 | Conceptual Beam Dump engineering design
10 | Risk Mitigation | 82 | Impact of apertures on SUSY
10 | Risk Mitigation | 83 | Estimate uncertainty in rate of incoherent pair production and impact on VXD-Layer 1
10 | Risk Mitigation | 84 | Continue study of how shape of bhabha energy distribution as measured in forward calorimeters is measure of cms Energy
10 | Risk Mitigation | 85 | Continue study of how to infer CMS energy from measurements of radiative returns to the Z [ee -> (Z -> ll,qq) g]
10 | Risk Mitigation | 86 | Continue study of how to infer the event boost which results from the ISR and beamstrahlung using measurements of the acollinearity in Bhabha events
10 | Risk Mitigation | 87 | Define energy measurement scenario using the complementary information from beam and physics measurements
10 | Risk Mitigation | 88 | Use LAT to measure Bhabha cross-section - Provide hermetic calorimetric coverage (83.8 to 27.5 mrad)
10 | Risk Mitigation | 89 | Use LCAL to measure pairs and track fast luminosity changes - Provide hermetic calorimetric coverage (30 to 5.4 mrad)
10 | Risk Mitigation | 90 | Continue analysis of ee -> WW and ee -> Wen processes for polarization information
10 | Risk Mitigation | 91 | BeamCal performance study and conceptual design
Note on B5: Thomas W Markiewicz: To set up which tasks affect which choice I began by listing all current tasks; have had time to only weakly edit the first two Choice, but you get the idea. This exercise tells me we need some new "Choice" categories.